## Slide 1
JOHN HONEYCUTT
Program Manager
NASA’s Space Launch System
NASA’s
Space launch System
Progress Report
October 21, 2019
Notes: NOTE: This presentation was developed for John Honeycutt for the 70th International Aeronautical Conference, Oct. 21-25, 2019 in Washington, D.C.
Welcome the audience.
I’d like to outline for this presentation on the progress SLS has made over the past year and the road ahead.
We’ve made a lot of progress since the conferences a few years ago where most of our slides were artist’s concepts.
I’ll talk briefly about the larger context for SLS and then spend the rest of my time on progress and the future.

## Slide 2: ARTEMIS PHASE I: TO THE LUNAR SURFACE BY 2014
Notes: SLS is part of a larger lunar campaign. The first phase is humans on the Moon by 2024. The second is expansion of that presence.
SLS will fly:
Artemis 1 = test flight
Artemis 2 = crewed lunar flyby
Artemis 3 = first woman, next man to walk on the Moon
SLS is the only rocket with the power and capability required to carry astronauts to deep space on the Orion crew vehicle.
Commercial will also have role to play with transportation of Gateway and lander components.

## Slide 3: SLS Evolvability Foundation for a generation of deep space exploration
Payload to TLI/Moon
355 ft.
RS-25 Engines
365 ft.
Core Stage
Up to 313ft.
Interstage
Evolved
Boosters
Solid
Rocket
Boosters
Exploration Upper Stage
325 ft.
Orion
Launch Abort System
Launch Vehicle
Stage Adapter
Interim Cryogenic
Propulsion Stage
8.4m Fairing
Long (Up to 90’)
Solid
Rocket
Boosters
Core Stage
Interstage
Exploration Upper Stage
8.4m Fairing
Short (Up to 63’)
Universal
Stage Adapter
Core Stage
Interstage
Exploration Upper Stage
365 ft.
> 45 t (99k lbs)
37–40 t (81k–88k lbs)
34–37 t (74k–81k lbs)
> 26 t (57k lbs)
> 45 t (99k lbs)
SLS Block 2 Cargo
SLS Block 1B Cargo
SLS Block 1B Crew
SLS Block 1 Cargo
SLS Block 2 Crew
RS-25 Engines
SLS Block 1
> 26 t (57k lbs)
5m Class Fairing
(up to 63’)
322 ft.
Universal
Stage Adapter
Notes: NASA Marshall is building the most powerful rocket ever built, the Space Launch System, which is the only exploration-class vehicle capable of sending humans to deep space and the large systems necessary to live and work in deep space.
As shown here, the basic SLS design has room to grow in both volume and mass capability for both crew and cargo versions. We are laser-focused right now on the Block 1 crew version on the far left.
SLS has the power and capacity to lift large and complex payloads, reducing the number of launches needed to put hardware into space – and decreasing design complexity and operational risk by minimizing on-orbit operations.
SLS Block 1, with four RS-25’s and two 5-segment solid rocket boosters:
weighs 2.6 million kilograms (5.75 million pounds) fueled & stands 98.2 meters (322 feet) tall. It will carry 95 metric tons (over 209,000 pounds) LEO. Or more importantly to Artemis more than 26 metric tons (more than 57,000 pounds) to the Moon.
SLS Block 1B will upgrade with the Exploration Upper Stage and will be able to carry a co-manifested payload plus Orion. It will likely be the first variant to use our new restart RS-25 engines with 111% thrust vs. 109% for the heritage engines. It will also likely be the first to use the more powerful Booster Obsolescence and Life Extension - or BOLE – solid rocket boosters once our heritage inventory runs out. The result will be a vehicle with 105 metric tons (>231,000 pounds) to LEO and 35 to 40 metric tons (roughly 75,000 to 88,000 pounds) to the Moon – depending on crew or cargo configuration and other ongoing design trades.
SLS Block 2 will have advanced boosters and will be able to carry roughly 130 metric tons (286,000 pounds) to LEO or more than 45 metric tons (99,000 pounds) to TLI.
These are not just nice numbers. This capability changes your whole architecture and the risk associated with it – for the better.

## Slide 4: NASA’S SPACE LAUNCH SYSTEM BACKBONE OF DEEP SPACE EXPLORATION
Launch Abort System (LAS)
RS-25 Engine (4)
Aerojet Rocketdyne
Service Module (SM)
Spacecraft Adapter
5 Segment Solid Rocket Booster (2)
Northrop Grumman
Interim Cryogenic
Propulsion Stage (ICPS)
Boeing/United Launch Alliance
Encapsulated Service Module (ESM) Panels
Crew Module (CM)
Launch Vehicle Stage Adapter
Teledyne Brown Engineering
Orion Stage Adapter
Core Stage & Avionics
Boeing
RL10 Engine
Aerojet Rocketdyne
Orion Multi-Purpose
Crew Vehicle
Lockheed Martin
BLOCK 1 CONFIGURATION
Notes: Let’s take a look at the SLS configuration for our maiden Artemis 1 mission:
Block 1 will be more capable than any current launch vehicle, able to deliver >26 metric tons (57,320 lb) to the Moon.
Visible are the major elements of the Artemis 1 vehicle – solid rocket boosters, core stage, (engine section, LH tank, intertank, LOX tank, forward skirt) LVSA and ICPS, OSA, and Orion/SM/LAS.
The investments in design, testing, tooling and lessons learned on Block 1 apply directly to future configurations based on Block 1.

## Slide 5: ARTEMIS i SOLID ROCKET BOOSTERS COMPLETE
Notes: SLS boosters leverage shuttle boosters
Five segments, instead of four
All-new avionics, asbestos-free insulation
All 10 motor segments complete for Artemis 1
Motor casting for Artemis 2 complete
Artemis I forward, aft assemblies nearing completion at KSC
Preparing to ship motor segments
Artemis 1 booster nozzles, separation motors complete
Avionics qualification testing at MSFC complete
Booster fast facts [if needed]:
Prime contractor Northrop Grumman
Each 177 feet or 17 stories tall – taller than the Statue of Liberty
Each is 12 feet in diameter
Each booster burns through 1,385,000 pounds of propellant in two minutes – an average of 5.5 tons of propellant every second
Each booster’s thrust is greater than 14 four-engine Boeing 747s at full take-off power
During flight, the temperature of the motor chamber gases reach more than 5,000°F – hot enough to boil steel!

## Slide 6: Artemis I RS-25 flight engines complete
Notes: All four engines complete for Artemis 1, shipped from MAF to SSC, MAF has done 3 engine pathfinder install/removal tests
Engine installation begins in Oct!
There are 256 engine install steps for the entire 4-engine cluster.
Program has been hot-fire testing the RS-25 engines since 2015 to ensure the engines can perform under the different SLS pre-launch conditions, higher heating environment, and flight thrust profiles, and also to qualify the new controllers
32 tests and more than nearly 15,000 seconds hot fire time so far
Engine Fast Facts:
4 RS-25 engines vs 3 for shuttle,
109% thrust vs 104.5%,
new controller and software and nozzle insulation,
more than 500,000 lbs thrust each, more than 1 million seconds total ground and flight time
Program began with 14 flown engines and 2 new serial number engines built from spares to support first 4 flights.

## Slide 7: ARTEMIS I CORE STAGE ASSEMBLED
Notes: Engine section mated to rest of stage on Sept 19.
Boeing will begin installation of RS-25 engines October
After closeout work to connect wiring, piping, ductwork, check avionics, and Final Integrated Functional Test, the completed stage will ship to Stennis for “green run” testing
Artemis 1 core stage manufacturing is 90 percent complete with first production-unit issues behind us.
The complex engine section is complete, tested and mated with the other 4/5 of complete Core Stage 1.
The Boeing Stage Controller test team recently began integrating the Stage Controller to the System Integration Test Facility-Qualification (SITFQ) ring in support of risk reduction testing for Stage Controller validation testing. This will be the first time the Stage Controller has been connected to non-simulation avionics equipment in this configuration. The test team will continue to add complexity in the connections in a phased approach.
Core Stage Fast Facts:
All-new development
212 feet long
27 feet diameter
Empty Weight: ~188,000 lbs (85,275 kg)
LH2 capacity: Up to 537,000 gallons (2 million liters) (317,000 pounds)
LOX: 196,000 gallons (742,000 liters) (1.86 million pounds)

## Slide 8: CORE STAGE STRUCTURAL TESTING
Notes: The largest structural testing campaign since the Space Shuttle Program is at least 80 percent complete
Hundreds of tests at every level of development – basic materials to flight hardware, subscale to full scale, development to qualification testing.
Major highlights:
Four full-scale Core Stage STAs
Built or refurbished four test stands @ MSFC
Engine Section STA arrived May 2017; testing finished; ~ 36 tests and 2,500 channels of data
Intertank STA arrived March 2018; testing finished ~ 21 influence, 18 limit, 2 ultimate, 1 test to failure, more than 2,800 channels of data
LH2 STA arrived Jan ‘19 (during furlough); structural testing in progress. ~38 test cases, more than 3,900 data channels, primary influence testing complete, green run test case complete, influence test cases complete early August. Remaining margin testing continuing through October
LOX STA arrived July 2019; Tests started this month: ~24 load cases and more than 2,600 data channels
Also completed the Integrated Structural Test of the ICPS, Orion Stage Adapter, LVSA stack in 2017. Roughly 50 tests with 1800 channels of data. Loads >40% above flight loads
This chart that doesn’t fully tell the story of the hundreds of tests we’ve done at every level of development – from basic materials to flight hardware, subscale to full scale, development to qualification testing.

## Slide 9: B-2 STAND READY FOR GrEen run
Notes: Here you see the core stage pathfinder, a full-scale mockup simulating the shape, size, weight and center-of-gravity of the flight hardware in the B-2 test stand at Stennis
Crews practiced lifts and other maneuvers with the Pathfinder before the Artemis 1 flight stage arrives in December.
Pathfinder is now at KSC for similar handling maneuvers and training.
Green Run validates the core stage design, performance and workmanship and verifies the readiness of the stage to be shipped to KSC for final processing and integration before launch
Green Run includes several first-time events for the world’s largest rocket stage:
First propellant fill-up for the LOX and LH2 tanks
First end-to-end flow test of propellants and other fluids through the complete stage
First operational test of flight avionics
First firing of all four RS-25 engines together
First use of B2 Test stand in this configuration
In addition to the hot fire, other tests as part of Green Run may include vibration testing, leak and functional checks, hydraulics and thrust vector control, safing, simulated countdown and wet dress rehearsal during which propellants are flowed through the stage but not ignited
The program is evaluating options for accelerating the Green Run campaign.

## Slide 10: ARTEMIS I INTERIM CRYOGENIC PROPULSION STAGE COMPLETE
Notes: ICPS and OSA shipped to KSC in 2017 and 2018 and stored in the Space Station Processing Facility. ICPS stages will power the first 3 SLS missions.
ICPS is largely a modified existing stage:
Background: Built by Boeing/ULA
modified Delta Cryogenic Second Stage by lengthening LH2 tank, adding hydrazine bottles for attitude control and minor avionics changes
42’ tall x 16’ wide
Powered by one AR RL-10B-2 engine/LH2/LOX
24,750 lbs thrust
Provides TLI burn for Orion (Artemis 1)

## Slide 11: ARTEMIS I STAGE ADAPTERS STATUSCOMPLETE
Notes: On the left top and bottom, the Orion Stage adapter being shipped to KSC and a look inside at MSFC with the brackets for the secondary payload deployment system
Right: LVSA when it was moved to 4649 for final processing; installed FJA and PAS; performed leak checks; installing DFI, doing final closeouts; scheduled to ship to KSC next year.
LVSA Fast Facts:
Connects core and upper stages
27.5’ long and 27.5’ wide at base, tapers to 5 m at top
Friction-stir welded lightweight aluminum alloy
Manufactured by Teledyne Brown @ MSFC
OSA Fast Facts:
Connects ICPS and Orion
5’ high, ~18’ diameter
Holds 13 cubesats and avionics unit for Artemis 1

## Slide 12: REMAINING STEPS TO FINAL INTEGRATION
BOOSTERS: Deliver forward & aft assemblies, ship motor segments; crews maneuvering pathfinders in RPSF
CORE STAGE: Engine installation, shipping to SSC, Green Run test campaign, shipping to KSC
LAUNCH VEHICLE STAGE ADAPTER: Install DFI, quick disconnects & cable runs; final checkout; shipping
SYSTEMS ENGINEERING & INTEGRATION: DCR, flight software delivery, Software Integration Lab (SIL) certification, CoFR, training
Notes: Hit some highlights of remaining work before we start integrating the vehicle in the VAB.
BOOSTERS: Deliver forward & aft assemblies, ship motor segments; crews maneuvering pathfinders in RPSF
CORE STAGE: Engine installation, shipping to SSC, Green Run test campaign, shipping to KSC
LAUNCH VEHICLE STAGE ADAPTER: Install DFI, quick disconnects & cable runs; final checkout; shipping
SYSTEMS ENGINEERING & INTEGRATION: DCR, flight software delivery, Software Integration Lab (SIL) certification, CoFR, training

## Slide 13: SLS PROGRESS TOWARD ARTEMIS II
All booster motor segments cast
Liquid oxygen tank
LVSA, OSA panels
Liquid hydrogen tank
Forward skirt
Two RS-25s complete, controllers green run
Engine Section
Notes: Lots of progress toward second flight:
Top left: All booster motor segments cast for second flight; 5 complete in barn
CS2: All components manufactured
Bottom: LVSA and OSA panels machined at AMRO; 4 LVSA-2 panels delivered to MSFC; Janicki working OSA-2 diaphragm
Bottom left: Two flight engines complete and stored in place; all controllers green run
An extra word about core stage manufacturing for Artemis 2:
We are benefiting from a steady stream of process improvements. Each step in production has been analyzed and streamlined. As a result, although we have prioritized our resources to completion of the Artemis 1 core stage, the Artemis 2 core stage production schedule currently is averaging 50% improvement in schedule over the Artemis 1 core stage. For example, we have so far seen a 70% improvement in labor hours on the engine section and 33% improvement on the intertank.
If you drill down into those numbers, you can see several factors in that improvement. For example, in the engine section, the most complex section of the core stage, we have seen a significant improvement in manufacturing discrepancies, a 97% improvement in rework hours and an overall 70% improvement in baseline labor hours required.
Those improvements are the result of numerous process improvements. Some of those are: shorter, more precise work instructions; a new one-shot drilling technique; thermal protection system application improvements; sensor installation improvements; a new job kitting process that has parts, tools and instructions ready when each shift arrives for work; implementing standard rework techniques; and placing NASA program management in the factory to accelerate decision-making.

## Slide 14: THIRD FLIGHT AND BEYOND
Five RL-10s complete
Booster processing
Payload adapter manufacturing demonstration article
Additively manufactured pogo accumulator
RS-25 HIP-bonded main combustion chamber
Tooling for USA
EUS weld confidence articles
Notes: Significant progress toward Artemis III and future flights, including Block 1B
Top left: Five RL-10s complete for EUS.
Top center: Boosters processing and casting for third flight, as well as FSB-1
Top right: Payload adapter manufacturing work @ MSFC
Bottom right: Much work is under way on developing a new more affordable, expendable variant of the RS-25 that costs at least 33 percent less and operates at 111% (521,000 lbs) thrust
It incorporates new materials and new manufacturing processes, as well as new technology like 3D printing. The latest test series beginning in 2018 includes a 3D printed pogo accumulator and a hot isostatic pressure (HIP) bonded main combustion chamber (bottom left);18-engine follow-on contract in progress
Bottom center: EUS weld confidence articles: on the right is a ring segment; left is a barrel panel.

## Slide 15
Notes: Progress Video [music, no narration] 1:30
One last live look at real flight hardware for the first Artemis mission.
The payoff for years of hard work. This animation will soon be real.
Artemis 1 Booster segments being cast and transported at Northrop Grumman in Utah
Full scale qualification solid rocket motor test firing in Utah – booster throat plug dispersion high speed video
Artemis 1 Flight engines at Michoud
Adaptation and controller green run testing at Stennis
Artemis 1 core stage forward join (forward skirt, LOX tank, intertank) mate at Michoud
Artemis 1 forward join to LH2 tank mate at Michoud
Artemis 1 core stage to engine section mate at Michoud
Artemis 1 LVSA transported at MSFC
Artemis 1 ICPS at ULA in Decatur, AL
Artemis 1 ICPS at KSC
OSA to the Super Guppy at MSFC
LH2 and then LOX structural test articles at Michoud and then installation in stands at MSFC
Core Stage Pathfinder installed in B2 stand at Stennis
Finally the moment we’re all working toward at KSC

## Slide 17
www.nasa.gov
@NASA_SLS
NASASLS
youtube.com/nasa
@explorenasa
Notes: Best way to keep up to date is to follow us on social media.
For each step of completion of the core stage, we’re posting pictures on social media and the web page.
Remind audience of major points:
Artemis 1 vehicle nearing completion
Core stage will ship from factory in a few months
Green Run next year then on to final integration at KSC
Well-positioned to deliver second and third vehicles in a much shorter timeline
Work on EUS is continuing
Thank audience for their time and offer to answer questions