# NASA Space Launch System Completes Green Run Testing, Begins Assembly

By John Honeycutt, Chris Cianciola, Dr. John Blevins, Johnny Heflin, Bruce Tiller

Space Launch System Program

NASA Marshall Space Flight Center

NASA’s Space Launch System (SLS) Program is poised in 2021 to shift its focus to the launch site with the completion of its last major integrated hardware and software test.

SLS is NASA’s evolvable super heavy-lift launch vehicle for deep space exploration. Using proven propulsion technologies, SLS will be the most powerful launch vehicle in the world. That capability translates not only into more mass and volume to destinations but also simplified payload design and mission operations and greater opportunity for mission success.

These capabilities will be important for the Artemis program, NASA’s plan to return humans to the Moon to stay in a sustainable way in order to develop and test technologies and operations needed for human missions to Mars and other destinations. SLS will anchor the transportation leg of an innovative, sustainable program of lunar exploration with commercial and international partners as the first step of human exploration of deep space.

While all major hardware and software efforts made significant progress in 2020 and 2021, the most visible was the Green Run test series of the Artemis I core stage conducted at NASA’s Stennis Space Center (SSC) on the B-2 test stand. The series validated core stage design, performance, workmanship, and readiness for shipment to NASA Kennedy Space Center (KSC) for final processing, integration and launch. The core stage provides the backbone for SLS’ main propulsion system, consisting of two five-segment solid rocket boosters and four RS-25 liquid hydrogen (LH2)/liquid oxygen (LOX) engines. SLS also includes an Interim Cryogenic Propulsion Stage (ICPS) that will insert the Orion crew spacecraft into a lunar trajectory.

The Green Run series represented several significant first-time events for the SLS core stage, the world’s largest rocket stage. The series consisted of eight separate test cases: modal, avionics, vehicle safing, main propulsion system, Thrust Vector Control/hydraulic, simulated countdown, wet dress rehearsal, and hotfire. At the time of this abstract, the NASA/Boeing/Aerojet Rocketdyne team had completed seven tests and was preparing for a second hotfire test to obtain data not collected when the first hotfire aborted 61 seconds into a planned 500-second run designed to simulate a typical SLS mission from launch to main engine cutoff (MECO). The stage remained in excellent condition with only minor repairs required before a second hotfire to collect additional data. Pending the outcome of the test, the stage is scheduled for inspection and minimal refurbishment before shipment to KSC for a launch targeted for late 2021.

Simultaneously at KSC, Jacobs technicians are stacking the Artemis I solid rocket boosters on the Mobile Launcher (ML) in the Vehicle Assembly Building (VAB) High Bay 3. In late 2020, crews began booster assembly by mating the aft segments of the five-segment boosters to the aft skirts and aft exit cones. Those aft assemblies were then mated to the ML. From there, crews lowered the center aft segments onto each aft assembly, followed by the center segments and center forward segments. The segments are bolted together and checked for leaks following each mating operation. The Artemis I forward assemblies have been transferred to EGS, and they are ready to be stacked on top of the motor segments, which will complete the booster stack.

Primary structures for the Artemis II core stage forward skirt, LOX and LH2 tanks, intertank and engine section are complete. The forward skirt is complete and ready for forward join, the operation that mates the forward skirt with the LOX tank and intertank. Forward skirt functional testing is complete and intertank functional testing is in progress. Although work on the Artemis II core stage is ongoing, managers expect a double-digit reduction in labor hours related to the learning curve, improved processes, and other changes.  The Artemis III core stage LH2 tank is structurally complete, as is the engine section barrel weld. Several affordability initiatives including design, producibility, safety, processes, safety and more offer additional improvements in cost and schedule.

The Artemis II solid rocket motor segments also are complete. The booster team has developed its launch control display screens and countdown book for the Artemis I launch, and console personnel training simulations are underway.  To date, all major hardware deliveries have adequate schedule margin to support Artemis II and Artemis III plans. Lessons learned from Artemis I booster manufacture and processing are positively influencing Artemis II with labor savings ranging from five percent for booster separation motor buildup to 74 percent for aft skirt assembly mechanical buildup.

The Artemis I core stage RS-25 engines have performed nominally throughout the core stage green run test series, and post-hotfire refurbishment processing is on schedule. The Artemis II engines are processed and ready to ship to Michoud in 2021. Artemis III engine assembly is progressing ahead of need. The SLS/Aerojet Rocketdyne team has started the Retrofit 2 hotfire test series  at SSC with the first test of ground test engine #0528 modified with several pieces of development hardware for new production RS-25 engines, including a Hot Isostatic Pressure (HIP)-bonded main combustion chamber and additively manufactured parts among them. The program is on target for an affordability goal of an engine costing at least 30 percent less than its shuttle predecessor. Production of the Artemis V RS-25 flight set is making steady progress. An 18-engine contract is in place to support SLS flights throughout the 2020s, with deliveries aligned to upcoming missions.

In the upper stage/payloads part of the SLS Program, the Artemis I ICPS is complete and being prepped for hydrazine fueling at KSC prior to integration with the rest of the SLS stack. The Artemis II ICPS is in construction at Boeing/ULA. RL10 engines to support the first three SLS flights are complete as are the first set of RL10s for the Exploration Upper Stage (EUS) that will replace the ICPS on the fourth SLS mission. The EUS passed its Critical Design Review (CDR) in December 2020. Planning is underway for EUS production and sea level engine testing.

The Artemis I Orion Stage Adapter (OSA) and Launch Vehicle Stage Adapter (LVSA) are both at KSC awaiting integration. The CubeSat payloads manifested on the Artemis I flight will be stowed in the OSA. Integration operations to install the payloads in commercial off-the-shelf (COTS) dispensers are scheduled to begin by mid-2021 at KSC. Artemis II adapters are in manufacturing at Marshall Space Flight Center’s Advanced Weld Facility using self-reacting friction-stir welding. Panels for the adapters for the Artemis III flight are in production.

This paper will discuss 2020-2021 SLS progress in greater detail, as well as plans for the upcoming Artemis I vehicle integration and manufacturing of the Artemis II and subsequent vehicles.