## Slide 1
Space Technology Mission Directorate
Game Changing Development Program
Aaron Paz| Carbothermal Reduction Demonstration (CaRD)| NASA APL ISRU Technology Review | 08.17.2022

## Slide 2: Introduction – Oxygen from Regolith (O2FR) Demonstrations
2010
Solar Concentrator - PSI
Carbothermal Reduction Module- Orbitec
Thermal Power
Excavator - CSA
Regolith
Hydrogen
Water
Water Electrolyzer – NASA
Thermal Power
Oxygen
Cryocart–NASA
Sintered Landing Pad
Fire
Water
Hydrogen
H2 Storage - NASA
Fuel Cell - CSA
CaRD project intends to raise the TRL of an integrated solar concentrator/carbothermal reactor/gas analysis system in order to propose a flight demonstration that uses actual lunar regolith and solar flux at the lunar poles
CaRD
2008
PILOT-Lockheed Martin
ROxygen-NASA

## Slide 3
Tracking Mechanism
2.Optical waveguide (fiber optic bundle) carries concentrated light to reactor
Solar Light
Reaction
Products
Gas Analysis
3. Concentrated light melts regolith. Carbothermic reaction removes oxygen from silicate minerals in the form of CO
Solar concentrator focuses light and directs it into optical waveguide
4. Mass spectrometer is used to determine the amount of CO produced from the reaction
Light
Image: Section view of 2010 field demo reactor
Introduction – Simplified CaRD Conops

## Slide 4
Introduction – Why Carbothermal?
Carbothermal Reduction is the only O2FR method with the following combination of factors
Has demonstrated automated transportation of regolith into and out of the reaction zone
Has been demonstrated at a relevant scale
Can be applied anywhere on the lunar surface
End-to-end
Lunar Carbothermal O2FR Process
O2 Liquefaction & Maintenance
O2 Dryer
Inlet Hopper
Soil Excavation
Water Electrolysis
Condenser
Outlet Hopper
Spent Soil Disposal
Water Cleanup
Carbothermal Reactor
H2O
CH4
H2
H2O
O2
CH4, CO, H2, CO2
CH4
Common to Mars ISRU, Carbothermal and ECLSS
Sabatier Reactor
Methane Gas
Common to Mars ISRU and Carbothermal
End-to-end
Mars Propellant Production Process
O2 Liquefaction & Maintenance
O2 Dryer
Inlet Hopper
Soil Excavation
Water Electrolysis
Condenser
Outlet Hopper
Spent Soil Disposal
Water Cleanup
Regolith Dryer
H2O
CH4
H2
H2O
O2
Sabatier Reactor
CH4 Liquefaction & Maintenance
CH4 Dryer
CH4
CO2
CO2 Collection
Dust Filtration
H2O
Has commonality with Mars ISRU
Has commonality with ECLSS

## Slide 5
Project Overview
Technology Product Capability
  Oxygen from Regolith (O2FR) technology development effort that can transition to mid-size CLPS payload upon completion of the project
  Integrated demonstration of solar concentrator, carbothermal reactor, and gas analysis system in a relevant environment
Technical Capabilities
  Light-weight deployable solar concentrator heats regolith beyond melting point
  Concentrated solar energy is routed through fiber optic cable (developed through SBIR program) to carbothermal reactor
  Automated O2FR process (developed through Tipping Point) receives concentrated solar energy where regolith is melted
  Reaction products are analyzed using modified COTS mass spectrometer
Exploration & Science Applicability
  This technology has the potential to produce several times its own weight in oxygen once deployed on the lunar surface, enabling long term habitability of the moon with minimal dependence on earth resupply
  Prospecting missions are not required to begin deploying this technology at a useful scale on the lunar surface
  Carbothermal reduction has commonality with Mars ISRU and ECLSS systems
Notes: Provide an overview of the Project/Task
  The slide content is intended to remain static unless significant changes are made to the Project
  Pictures are encouraged, please provide new pictures as frequently as possible

## Slide 6: Team Members / Project Org Slide
1.0 Project Management
Aaron Paz
3.0 Integration
Aaron Paz
1.2 KSC PM
Annie Meier
4.2 TVAC Tests Thomas Viviano
4.3 Test Director Anastasia Ford
3.1 Fluids
Naina Noorani
3.2 Optical
Desmond O’Connor
3.3 Thermal
Lisa Erickson
4.0 Testing
Mike Reddington
5.0 Solar Concentrator
Tony Colozza
5.1 Optical Waveguide
Luis Rodriguez
6.0 Carbothermal Reactor
Diane Linne
7.0 Chemistry
Trey Barnes
8.0 Avionics
Chris Bond
9.0 Software
Jim Kania
Nilab Azim
Jennifer Williams
Alex Decamargo
Beau Peacock
Ryan O’Farrell
Kevin Smith
Optical Waveguide
Bill Kessler
Carbothermal Reactor
Brant White
1.1 GRC PM
Erica Montbach
Nathaniel Cain
Stephen Simmons
Joel Olson
Ray Pitts
Monique Moore
2.0 Systems Engineering
Aaron Paz
2.1 KSC SE
Jonathan Martinez
Mac Zborowski
Lawrence Kren
Rick Wainner
Takashi Nakamura
Will Clark
Kristin Galbally-Kinney
Rick Burkholder
Nathan Haggerty
Matthew Bair
Pat Verstegen
Bob Youngquist
ISRU SCL
(Jerry Sanders)
ISRU TIM
(Omar Hatamleh)
Program Element
Manager
(QuynhGaio Nguyen)
ISRU SCL Deputy
(Julie Kleinhenz)
STMD Interfaces
NASA Headquarters
Johnson Space Center
Glenn Research Center
Kennedy Space Center
Physical Sciences Inc.
Sierra Space Corp.
LOWE PM (Koorosh Araghi)
Notes: If you have submitted a Project Plan, you could utilize the Organizational Chart found in section 8.3 – Management Structure

## Slide 7: Collaborations & Partnerships
Collaborative multidisciplinary partnerships to leverage fiscal resources, ideas, knowledge & expertise.
SBIR/STTR
Physical Sciences Inc. (Phase 2 80NSSC20C0201)
Sierra Space (Phase 3 80NSSC20C0048)
NASA Centers
GRC
JSC
KSC
Public/Private Partnerships
Sierra Space
Contributing partners
  JSC Engineering has contributed ~500K
  Sierra Space contribution toward Tipping Point contract is ~850K
Infusion/transition plan
  Subscale ground demonstration
  Subscale flight demonstration
  Pilot Plant demonstration
  Full scale demonstration

## Slide 8: Project Goals
Draft Goals (Project Plan in Work) | 
Goal #1 | Raise TRL of individual components within two years to allow for maximum flexibility and de-scope options.
Goal #2 | Raise TRL of an integrated Carbothermal reduction system to TRL6 by performing a ground demonstration in a relevant environment.
Goal #3 | Develop a systems engineering framework for an O2FR ground demonstration that prepares team for flight demo opportunities.
Goal #4 | Utilize model-based systems engineering for requirements development and SE products that can be applied to future ISRU projects and flight demonstrations.
Need
In April 2020, NASA submitted the Plan for Sustained Lunar Exploration and Development to the National Space Council. The report defines several goals for the Artemis Program and states that “ISRU will enable the production of fuel, water, and/or oxygen from local materials, enabling sustainable surface operations with decreasing supply needs from Earth.”

## Slide 9: Project Objectives
Draft Objectives (Project Plan in Work) | 
Objective #1 | Develop Mission Concept Review (MCR) products per NPR 7123.1C but apply them to a ground demonstration in a relevant environment.
Objective #2 | Develop preliminary requirements for ground demonstration based on environmental requirements for previous lunar surface missions and NASA standards.
Objective #3 | System Requirements Review (SRR)
Objective #4 | Preliminary Design Review (PDR)
Objective #5 | Critical Design Review (CDR)
Objective #6 | Develop engineering test units (brassboards)
Objective #7 | Test brassboards in a thermal vacuum chamber (TRL 5)
Objective #8 | Develop integrated prototype system
Objective #9 | Test integrated prototype system in thermal vacuum chamber (TRL6)
Objective #10 | Final report

## Slide 10: TRL Progression CaRD
FY22 | FY23 | FY24
Project Milestone
GCD (Key) Milestone
Controlled Milestone
TRL/SRL/MRL Progression
TRL
6
KCTE-3 Optical Waveguide Subsystem
5
4
KCTE-4 Gas Analysis Subsystem
Integrated Brassboard TVAC Test
KCTE-2 Solar Concentrator Subsystem
Solar Concentrator Thermal Cycle Test
Integrated Prototype TVAC Test
KCTE-1 Prototype System
Laser Vacuum Test
KCTE-5 Lander to System Interface
KCTE-6 Solar Concentrator to Optical Waveguide Interface
KCTE-7 Optical Waveguide to Carbothermal Reactor Interface
KCTE-8 Carbothermal Reactor to Gas Analysis Interface
Calibration Test
Integrated Prototype Test (Ambient)
Notes: Chart purpose: show TRL/SRL/MRL advancement over the project lifecycle schedule. Show TRL advancements as whole integer increases. Show how Key and Controlled milestones align with TRL advancement.
  TRL/SRL/MRL may not advance at each milestone. Often several milestones are required to produce a step increase in TRL/SRL/MRL.
There can be one, or more, of these charts per project as needed.
  For projects with fewer technical elements, the TRL/SRL/MRL data can be combined on one chart.
  For more complex projects, the TRL/SRL/MRL progression can separated into multiple charts by project technical area.
Show TRL, SRL, and MRL data for each technical element on the same chart.
  Delete TRL/SRL/MRL axis-labels that do not apply – e.g., remove SRL/MRL for projects/technical areas where SRL and MRL do not apply.

## Slide 11: Accomplishments
  Developed laser test stand with calorimeter
  Defined interface details between laser and vacuum chamber
  Laser support cart design, software, and structural analysis
  Completed carbothermal reactor testing
  Began gas analysis subsystem calibration
  Integrated CAD of vacuum test
  Completed integrated fluid system schematic
  Completed integrated electrical schematic
  Completed System Requirements Review
  Initiated composite mirror procurement
  Developed interface details between solar concentrator and fiber optics
  Developed solar concentrator deployment concept
  Completed checkout of laser and calorimeter
  Delivered laser to PSI for optical waveguide testing
Optical Waveguide Developed by PSI
2KW laser test stand with Calorimeter

## Slide 12: Accomplishments
Integrated Brassboard CAD
(isometric cross section view)
Carbothermal Reactor Developed by Sierra Space
  Developed laser test stand with calorimeter
  Defined interface details between laser and vacuum chamber
  Laser support cart design, software, and structural analysis
  Completed carbothermal reactor testing
  Began gas analysis subsystem calibration
  Integrated CAD of vacuum test
  Completed integrated fluid system schematic
  Completed integrated electrical schematic
  Completed System Requirements Review
  Initiated composite mirror procurement
  Developed interface details between solar concentrator and fiber optics
  Developed solar concentrator deployment concept
  Completed checkout of laser and calorimeter
  Delivered laser to PSI for optical waveguide testing

## Slide 13: Accomplishments
Solar concentrator stowed
Solar concentrator deployed
  Developed laser test stand with calorimeter
  Defined interface details between laser and vacuum chamber
  Laser support cart design, software, and structural analysis
  Completed carbothermal reactor testing
  Began gas analysis subsystem calibration
  Integrated CAD of vacuum test
  Completed integrated fluid system schematic
  Completed integrated electrical schematic
  Completed System Requirements Review
  Initiated composite mirror procurement
  Developed interface details between solar concentrator and fiber optics
  Developed solar concentrator deployment concept
  Completed checkout of laser and calorimeter
  Delivered laser to PSI for optical waveguide testing

## Slide 14: Project Assessment Summary
Project Name | Performance |  |  |  | Comments
 | C | S | T | P | 
Oct |  | LT |  |  | CR budget caused cost overruns and affected long term milestones
Nov |  | LT |  |  | CR budget caused cost overruns and affected long term milestones
Dec |  | LT |  |  | Funding drop fixed cost overruns, long term milestones still affected.
Jan |  | LT |  |  | PY21 funds for WYE near exhaustion
Feb |  |  |  |  | Enough funding was received to address overruns. Agreed to rebaseline long term milestones affected by CR budget in project plan.
Mar |  | NT |  |  | Funds for WYE support exhausted. Integrated brassboard test was affected.
Apr |  | NT |  |  | Guideline was reduced. Obligations exceeded guideline. Work stoppage issued
May |  | NT |  |  | Guideline was increased at the end of May, but funds were not distributed until June
June |  |  |  |  | Agreed to update integrated brassboard test completion milestone in project plan
July |  |  |  |  | Uncertainty around FY23 budget could affect Phase 2E/3 for optical waveguide prototype
LT = Long term (prototype) milestones affected.
NT= Near term (brassboard) milestones affected

## Slide 15: Infusion/Transition Plan
Moon to Mars Planning Manifest from FY23 NASA budget request summary
CT-1 Requirements for CLPS defined
CaRD Brassboard
CaRD Prototype
CLPS Lead Time (~3 years)
Included in CaRD project scope
Not Included in CaRD project scope
ISRU Subscale Demo Flight Hardware
Relevant Contracts not funded by CaRD
COPR-TP (Sierra Space)
Waveguide SBIR Phase 2 (PSI)

## Slide 16: Infusion/Transition Plan
Full Scale
10MT/yr
(2 kg/hr)
Pilot Plant
1MT/yr
(0.2 kg/hr)
CLPS Demo
(single melt)
Ground Demo
(single melt)
CLPS Demo 2026
Pilot Plant 2029
Full Scale Plant
COMPASS Study
3.5 MT/yr per module
SBIR Phase 3 (GRC-Sierra Space)
CaRD
SBIR Phase 3 (JSC-Sierra Space)
SBIR Phase 2 (PSI)
COPR TP(Sierra Space)
Studies/Development
Studies/Development
Ground Demo 2024
Requirements
Demonstrations
Completed
Active
Needed

## Slide 17: Summary
Team is on track to complete integrated brassboard test under vacuum in early FY23
Despite budget issues, the team was able to meet many technical objectives for the year. However, the reduced budget will result in a scope reduction for the prototype, as well as prototype milestone slips. The project plan in development will capture the scope and schedule going forward.