## Slide 1: Assessment of Aggregate Risk for JWST
Jesse Leitner, Chief Engineer, SMA Directorate
Tupper Hyde, Center Chief Engineer

## Slide 2: Outline
Background
Approach
Overview of risk picture
Accepted and open risks
Closed risks and closure process
Risks from late anomalies and failures
Assessment of current risk posture and aggregate risk
Summary

## Slide 3: Background
NASA’s ASAP panel was concerned about decisions made in testing in manned space flight applications that had major risk implications, without clear authority to do so or acknowledgment
A secondary concern was that higher levels of aggregate risk were missed by looking only at collections of smaller risks
NASA AA directed OSMA/System Safety to develop a clear means of accountability for decisions that involve risk and to ensure that aggregate risk is properly considered
NPR 8000.4 had been updated to formalize the approach
The magnitude, investment, complexity, and visibility of JWST combined with many late anomalies in development without complete resolution and/or complete regression testing prompt the need for an independent assessment of the overall risk picture for the mission.*
*See memo in backup

## Slide 4: BLUF
An independent review of JWST’s risk register has resulted in the following
  Determination that JWST’s capture, characterization, disposition, and communication of risks is complete and commensurate with a flagship Class A mission
  Potential aggregate risk statements to represent the cumulative technical risks on the observatory at the time of launch
  Determination that
    JWST’s observatory level testing is complete and ready for launch
    The late anomalies are artifacts of extensive handling and the testing of a zero-g observatory under the constraints of 1 g.
    Further deployment testing will likely expand on the issues above and more likely increase risk without any substantive improvement in confidence or reliability

## Slide 5: Approach
Perform a detailed, systematic, qualitative assessment of the JWST project risks and potential aggregate impacts, consistent with GSFC’s risk management approach
  Risk database as of December 2020 was used for this exercise and not ”refreshed” in this analysis
Steps were as follows
  Reviewed associated sets of open and closed risks to verify that they are commensurate with the risk picture for a project of complexity consistent with JWST, and that they are reflective of a sound risk management process.
  Reviewed associated sets of closed risks to ensure they indicate a proper closure process both holistically and on individual risks.
  Reviewed the open and accepted technical risks to determine whether there are clusters that could be collectively aggregated.
  Reviewed the collection of late anomalies and failures experienced that had corrections only verifiable at the component level because of risks to the observatory of further full-scale tests, for any supplemental risks that are solely due to the late nature.
  Constructed an overall statement of aggregate technical risk
It should be noted that the documents and databases reviewed are internal tools for risk management within the project and are not designed or formatted for external review.

## Slide 6: What is Risk?
Definition: the combination of
  a) the probability (qualitative or quantitative) that an undesired event will occur, and
  b) the consequence or impact of the undesired event
  c) a factual context or scenario that exists to cause the risk to be present
  In short, risk is an expectation of loss in statistical terms based an existing condition.
Categories of risk (consequences)
  Technical (failure or performance degradation on-orbit)
  Cost ($ it will take to fix the problem)
  Schedule (time to fix the problem)
  Safety (injury, death, or collateral damage)
This is the substantive version of a concern
The category may not match that of the concern
  Common: programmatic risk based on technical concern
programmatic
Notes: It is important to be explicit about what we mean when we say risk. This will be clear when we contrast risk with “possibility”.

## Slide 7: Risk Statement (GPR 7120.4D)
Given the [CONDITION*]
  There is a possibility that [INTERMEDIATE CONSEQUENCE] will occur
  Resulting in [CONSEQUENCE]
  CONDITION: A factual statement that describes the context that elevates the likelihood of a failure or shortfall. A system being single string does not automatically indicate that a risk is above baseline risk. What is the condition that exists that elevates the likelihood of failure?
  - there is a part installed that is a GIDEP direct hit
  - the supplier is located in a war zone
  - the expert personnel have just retired
  INTERMEDIATE CONSEQUENCE: The immediate, direct effect from a concern being realized
  - a part will fail
  - an item will be delivered late
  CONSEQUENCE: Foreseeable, negative impact(s) to meeting performance, programmatic, or safety requirements at the level of a project that is tracking the associated risk. Project level risks are threats to mission requirements.
  - instrument will fail
  - mission will fail
  - launch will slip
  - a person will be injured
*[CAPITALIZED] terms will be called fillable items

## Slide 8
Flight Project Risk Rating Scale

## Slide 9: Risk Terms in NASA
Baseline risk: the normal level of risk in developing and assembling a product
  This can be considered as risk that is accepted by a project at initiation without further tracking or debate
  Generally we do not track risks within the baseline
  Experienced developers mitigate baseline risks through standard processes
Credible risk: risk having likelihood category of at least “1” on the pertinent risk scale (note that in GSFC’s risk scale there are 5 categories and 1 is the lowest risk category)
  There are an infinite number of risks that are not credible for any project
Notes: These terms are used quite often within NASA but it is difficult or impossible to find definitions anywhere. A “1” on the likelihood scale does not mean likelihood of 1 (100%), but it means the lowest probability range given the particular risk type (technical, cost, schedule, safety). For a technical risk, 1 is from 0.1% to 2%.

## Slide 10: Risk Terms in NASA (cont’d)
Accept: Determine that the consequences of an identified risk, should they occur, are acceptable without further mitigation.
Close: Determine that a risk is no longer credible and tracking may be discontinued
Residual Risk: the remaining risk that exists after all mitigation actions have been implemented and/or exhausted in accordance with the RM process. Residual risks are often technical risks that are accepted at the time of launch. Often the term is used when an effort is complete to resolve a failure, anomaly, or nonconformance when resources are not available to completely resolve the concern or requirements shortfall.
Notes: These terms are used quite often within NASA but it is difficult or impossible to find definitions anywhere. A “1” on the likelihood scale does not mean likelihood of 1 (100%), but it means the lowest probability range given the particular risk type (technical, cost, schedule, safety). For a technical risk, 1 is from 0.1% to 2%.

## Slide 11: Overview of risk picture
JWST risk register illustrates a solid and complete understanding of broad concern and risk profile for the mission
The risk register has its foundation in the old “if, then” format risk statements and while the project changed to align with the new format years ago, the spirit of the old format remained (likely a cultural artifact).
Holistically demonstrates a well-thought-out assessment of the potential mission shortfalls
Risk database conservatively includes numerous “what-if?” risks that are remote possibilities
Risk database includes numerous “engineering work to go” risks that represent notable efforts outside of the baseline development plan
There are a handful of risks that are conservative placeholders just to make sure that a particular concern is not forgotten, even if the consequence is not clear
The vast majority of project risks are either non-credible risks or forms of communication that the project is paying attention to high profile items
There is a holistic and aggregate risk captured in the process that something may have been missed in the enormously complex system, with no holistic past history, and very limited ability to test as it is meant to be operated
The JWST risk picture and documentation thereof is on par with that of other NASA complex and critical missions

## Slide 12: Closed risks
There are no recently-closed risks (as of Dec 2020) for the project
  All closed risks date back to the old form of “if, then” statement
  The if, then form of risk constitutes more of a fact than a risk
Many of the closed old risks appear to have been brought in to the new risk construct if the context still existed
There are no “buried” items with improper closure in the set of closed risks

## Slide 13: Assessment of current risk posture
The current risk posture is largely characterized by accepted and open risks, but has the potential to be influenced by current issues that may ultimately not be fully resolved
At the lowest level, the key risk areas are as follows:
  Extensive use of NEA devices that have minimal fault tolerance, that are critical to the deployments, and that cannot be fully tested without “resetting”.
  The use of the new ¾” design NEA devices in critical applications without past flight history
    There was an extensive (multi-year) development program and a full qualification program
  The incorporation of NEAs into Membrane Release Devices (MRDs) that may add application risk.
    There was full qualification program at the MRD level
  The limited ability to test the enormous observatory based on both practical constraints and necessary response to issues identified late in development that preclude a complete test in flight configuration.
It is notable that a key design feature of the 1/8” devices returned to the proven heritage design, aligning better with the established reliability of common historical NEAs.

## Slide 14: Secondary Risk Areas
Minor instrument risks that result from modeling limitations (characterized by green risks)
Any remnant fasteners subject to the potential fastener torquing issue that were inaccessible and difficult to analyze, and only addressed through system-level testing. (absorbed in the aggregate risk statement)
  Observatory Sine Vibe / Acoustics
  Observatory Deployment
  Post Deployment Laser Alignment Measurements for Risk Mitigation
Any unresolved elements from the transponder issues
  Delta CST-5 and GSEG testing successfully completed
  Since repairs also included “touch up” of solder joints showing depletion, one could argue the transponders are in a better risk posture than before the repairs relative to aging.

## Slide 15: Risk from Late Anomalies and Failures
Since late 2019,there have been a number of failures and anomalies that have occurred that will not be able to have corrective actions verified from full observatory level tests (only local verifications). These are in the following categories:
  Tears in blanketing and sensitive membranes
  Cable tension and guiding sleeve issues
  Tolerance stackup issues covering the observatory
  Issues associated with effects of gravity (and associated offload)
For the first item, there is no indication of a systemic concern or risk associated with tears.
  They are a natural consequence of the extreme sensitivity of the blankets and membranes combined with the regular handling of the large observatory.
  This is best addressed by a comprehensive examination of all such surfaces at the last reasonable opportunity before preparing the observatory for launch.

## Slide 16: Candidate risk from Late Anomalies and Failures (cont’d)
To some extent the next three items all combine to characterize an inherent risk (sub-aggregate risk) for such a large observatory as follows:
  Given: the large and complex observatory designed for zero-g operation, with extensive mechanical interconnections, and the need for meticulous handling within the observatory
  There is a possibility that: the 1-g testing environment with limited ability to off-load gravity will give rise to a stacking and cabling discrepancy on-orbit that affects a key deployment,
  With the result that: several observatory functions will be degraded
  Risk is mitigated by margins related to stray light, image quality, and cryo thermal margins
Recommended LxC: 1x4
Closure on completion of on-orbit deployments

## Slide 17: Aggregate Risk Assessment
All risks were reviewed for aggregation
While there were a pair of NIRCAM-related items, one of those risks was degenerate, so there was no aggregate effect.
The primary candidates for aggregation involve the deployments, most notably the sunshield.
  There are several such risks, most of which overlap in some way, that relate to the fact that the observatory cannot be fully tested in final flight configuration, and does not have any prior heritage to put to rest any interactions that may not have been observed.
  There are many risks that are captured solely because they involve single point failures (which is not in itself a context for risk).

## Slide 18: Candidate comprehensive aggregate risk 1
Given: the massive size, complexity, development constraints, and one-of-a-kind nature (with no historical reliability) of the JWST observatory that prevent complete test as you fly verification and/or validation of complex models,
There is a possibility that: a key interaction that impacts system performance is not identified,
With the result that: mission performance will be moderately degraded.
Recommended LxC: 2x3
Closure on performance verification of instruments after commissioning

## Slide 19: Candidate comprehensive aggregate risk 2
Given: the massive size, complexity, development constraints, and one-of-a-kind nature (with no historical reliability) of the JWST observatory that prevent complete test as you fly verification and/or validation of complex models,
There is a possibility that: a key system interaction that is not accounted for or modeled with sufficient fidelity in the 1-g testing environment combined with limited ability to off-load gravity will give rise to a stacking and cabling discrepancy on-orbit that affects a key deployment,
With the result that: mission will fail to meet minimum success criteria
Recommended LxC: 1x5
Closure on successful on-orbit deployments

## Slide 20: Summary
The collection of open, closed, and accepted risks for the project are sufficient to characterize the risk picture and overall risk posture for the mission.
The risk database is largely characterized by risks that really represent a desire to communicate that the project is dealing with topics and requirements that have high visibility and those that are in place to make sure that some focused engineering processes are properly completed
The aggregation activity has identified that the primary space for aggregation is across a number of risks associated with the deployment challenges, minimal fault tolerance, and the limited ability to test in a near-flight configuration.
An all-encompassing risk pair have been identified to characterize the most pertinent risk for the project.
In general, the risk posture from an aggregate perspective is commensurate with the risk posture for massively complex and large, one-of-a-kind flagship missions.
JWST observatory testing is complete and ready for launch
While there is a concern that some issues have resulted from late testing, one must consider the fact that many of the issues actually result from the fact that the observatory is not (and cannot) be tested in its ultimate designed zero-g state as well as the excessive handling of the observatory. Therefore, further observatory level testing that involves any type of substantive handling has passed the point of diminishing returns, and thus would drive up risk more than it buys it down.

## Slide 21: Backup materials

## Slide 23: Anatomy of a Risk
Context
Structured risk statement
Likelihood
Consequence
Concern
Statistics
Impact/Criticality
Uncertainty

## Slide 24: Key Rules to follow
The CONDITION must exist today and should be indisputable
No conditional statements or risks should be in any of the fillable items (the condition is already included in the statement structure) – see example on p. 20
  Rationale: Conditional statements within the risk will result in arbitrary likelihoods and “risk of a risk” scenarios.
Avoid using multiple consequences in a single risk statement (see p. 21)
  Especially if they are different flavors (common) as risk scales are different
The CONSEQUENCE represents the category
Safety of your own hardware is in the category of technical or programmatic risk
Avoid using “loss of redundancy” as a risk consequence at the project level (project level risks should be threats to level 1 requirements)
  Can result in unbalanced risk by comparing one risk of loss of function to another with no effect on mission performance
  Loses the benefit of redundancy
If possible, avoid risks that suggest that your own project team is going to make bad decisions – better to address those concerns directly within the project.