## Slide 1: Agile Software Engineering in NASA’s Waterfall World
David Swartwout
GW Production Software Lead
20 February 2024

## Slide 2: Overview
Agenda:
  NASA Procedural Requirements
  Lifecycles
  Process Rigor
  JSC Engineering’s Agile Process Evolution
  Toolchain
  Following the NPR Lifecycle
    SRR to PDR
    PDR to CDR
    CDR to TRR
    TRR to SAR
  Closing Thoughts

## Slide 3: NASA Procedural Requirements
NASA projects are governed by NASA Procedural Requirements (NPR)
NPR 7120.5, NASA Space Flight Program and Project Management Requirements
NPR 7120.7, NASA Information Technology Program and Project Management Requirements
NPR 7120.8, NASA Research and Technology Program and Project Management Requirements
And the overarching Systems Engineering NPR
NPR 7123.1 NASA Systems Engineering Processes and Requirements
All of these NPRs describe a reasonably rigid Waterfall lifecycle
The Systems Engineering “V”
Milestone Gate Reviews
  SRR, PDR, CDR, etc.
  Tailorable Entrance/Exit Criteria
  Products required at each review

## Slide 4: NASA’s Software Engineering Requirements
Software Engineering process and product requirements, as a component of the overall project execution are then detailed in
NPR 7150.2, NASA Software Engineering Requirements
Guidelines are described in
NASA Software Engineering and Assurance Handbook, NASA-HDBK-2203
NPR 7150.2 describes the “what” that has to get done
  Document requirements
  Document design
  Perform testing
  Etc.
But luckily, it doesn’t describe the “how”
  Does not dictate format or templates
Though, NPR 7123.1 does tell you “when”
  Milestone review entrance criteria describe what products are needed for each review
    Software requirements at PDR
    Software design at CDR
    Etc.
Caution - some Centers may levy additional constraints via Center specific Procedural Requirements

## Slide 5: The Waterfall Lifecycle
Some challenges and pitfalls of Waterfall
It assumes you got it right the first time
Going back to earlier cycles is nearly impossible
It takes a very long time to learn what you don’t know
  Or what you didn’t get right in the previous cycles
Course corrections are hard
Feedback is slow

## Slide 6: Agile
Industry experience has shown that Agile project management can be highly successful
Cyclic
  Looking at all aspects each iteration
Faster to uncover issues and gaps
Burn down risk earlier
Quicker Feedback
  Drive metrics for faster decisions
Fosters collaboration
Incremental growth of knowledge

## Slide 7: How did we bridge the gap?
So, how did we achieve Agile software engineering within NASA’s NPR dictated waterfall lifecycle?

## Slide 8: Apply process rigor when it is important
Process rigor is important
  But only at the right time
The content of the artifacts detailed in the NPRs are important
  Requirements
  Design documentation
  Test plans and procedures
Agile software engineering is not the “wild west” of project management
  In my experience with Agile, there are more day to day process requirements than other non-Agile projects I have worked
  Daily feedback loops
  Metrics
Gateway
,
J. Devolites – Morpheus/AA2

## Slide 9: Evolution of JSC Engineering’s Agile Software Engineering Process
Morpheus Lander ~ 2010 - 2014
1st focused attempt with Agile
Highly successful R&D project
Class C software project
CMMI ML 2
Orion Ascent Abort – 2 ~ 2015 - 2019
Orion flight test of Launch Abort System
Class B safety critical software project
CMMI ML 3
Gateway Lunar Outpost ~ 2019 - today
Multiple contractors, multiple teams
Class A safety critical software projects
CMMI ML 3

## Slide 10: Our lifecycle focused Agile flow
Changing software team focus as project moves through 7123.1 lifecycle
Focus on meeting the intent of the milestone without spending wasted time writing documents
Make NPR required artifact development part of the standard development flow
  Updating the design documentation is part of closing each code implementation story
  Evolving definition of done for different story types as we move through development gates

## Slide 11: Our Solution Leverages Several Tool Ecosystems
Jira
  TestRay plugin
    Functional Requirements
    Non-Functional Requirements
    Test Cases
    Test Plans
    Test Automation
  Stories – Work code
  Epics – Use cases
  Tasks – Design work
  Scripting API back end for trace tables
  Release management
Confluence
  Design documentation
  Use case management
Gitlab
  Source code
  Continuous integration pipeline
Doxygen
  Design documentation
Jenkins
  Automated testing
Home grown scripts to tie it all together

## Slide 12: Team Focus: SRR to PDR
Requirements
Verification Planning
Architecture
Tool Chain
Use Case Based Advancement of System Capability

## Slide 13: Development of Software System Requirements (SRS)
Use con ops and operational use cases to drive requirements
  Higher level requirements
Computer Software Configuration Item (CSCI) requirements are defined in Jira
  The box shall …
  Utilizes new Jira ticket types from TestRay plugin
Stakeholders review and comment right in the tools
  Enhances collaboration and feedback
The actual SRS is a confluence page with the embedded Jira tickets
  Jira/TestRay allows management of requirements baselines
  Export to a PDF to support a “baseline” for lifecycle reviews
  Manage change traffic between versions using labels on the Jira requirements

## Slide 14: Test Planning and Development
Verification Statements are part of the Jira requirement ticket
Each requirement is broken down into one or more test cases
  Nominal
  Erroneous
  Boundary
  Etc.
Test cases are another Jira issue type from the TestRay tool set
Review and collaboration continue in Jira
PDF exports can be made as snapshot baselines for reviews
Plan automated testing architecture

## Slide 15: Software Architecture & Implementation
Even though there is a concentrated effort on requirements, we are still implementing capability
Stand up development environment
  Toolchain
    CI pipeline
  Lab
    Hardware in the loop – the earlier the better!
    Emulators
    Simulators
  Desktop development
    Virtual machines
    Docker images
Implement preliminary architecture
  All pieces of the architecture cycling in early development sprints

## Slide 16: Use Case Based Advancement of System Capability
Working with product owners and relevant stakeholders
  Determine list of operational use cases that can be reasonably developed and demonstrated at this phase of the lifecycle
    Use cases are peer reviewed
    Used for training and familiarization
  Helps to flush out requirements
  Helps to define interfaces
Advance hardware in the loop capabilities
  Understand simulation and emulation requirements
  Understand fidelity of hardware environment
Integrated demonstration of capabilities and regular cadence throughout the phase
  We chose a three-month integration cycle
  Based on a two-week team sprint cycle
Continuous Improvement of Tools and Processes
  Enhancing CI pipeline
  Development of emulators and simulators
  Lessons learned from prior phases
  Documenting process enhancements
  Updating templates

## Slide 17: Team Focus: PDR to CDR
Requirements Decomposition
Design Elaboration
Use Case Based Advancement of System Capability

## Slide 18: Application Requirements Decomposition
Structured design process to decompose box level CSCI requirements into multiple application-level computer software component (CSC) requirements
  Requirements based use cases drive system capabilities
  2nd tier requirements are also captured in Jira
  Designs are documented via organized confluence pages
    Structured templates to drive commonality
    Jira requirements are linked into confluence design for traceability
    Confluence allows for
      Version control
      Review / comments / collaboration
  Flushing out interface design to both external and internal components

## Slide 19: Design Products
All design artifacts are “organic” products that are created inline as part of the development process
  We don’t stop what we are doing to make a big Word document and a bunch of PowerPoint slides
Utilize Doxygen, Confluence exports, and Jira scripting to create the design package
  HTML based “clickable” package

## Slide 20: Trace Tables
NPR 7150.2 requires requirements and verifications traceability
  Depending on software classification
Utilizing custom Doxygen tags in the source code, along with Jira scripting we can generate tables for bi-directional traceability
  Requirement <–> Design <–> Code
  Requirement <–> Code <–> Test

## Slide 21: Use Case Based Advancement of System Capability
Working with product owners and relevant stakeholders
  Determine list of operational use cases that can be reasonably developed and demonstrated at this phase of the lifecycle
    Use cases are peer reviewed
    Used for training and familiarization
  Helps to clarify requirements
  Helps to understand interfaces
Advance hardware in the loop capabilities
  Develop simulation and emulation capabilities
  Enhance fidelity of hardware environment
Integrated demonstration of capabilities and regular cadence throughout the phase
  We chose a three-month integration cycle
  Based on a two-week team sprint cycle
Continuous Improvement of Tools and Processes
  Enhancing CI pipeline
  Development of emulators and simulators
  Lessons learned from prior phases
  Documenting process enhancements
  Updating templates

## Slide 22: Team Focus: CDR to TRR
Final Implementation of Design
Test Script Development
Continuous Integration Pipeline
Use Case Based Advancement of System Capability

## Slide 23: Closing Application Requirements
Implement the requirement, using the design document as a reference
  Update the design page in Confluence if necessary
Tag all source code functions implementing the requirement with custom Doxygen tag
Unit test all the functions in the implementation
Verify the implementation matches the design document
Update associated data products
  Table definitions
  Commands
  Telemetry
Peer Reviews

## Slide 24: Test Script Development
Using test case statements defined in Jira/TestRay
Structured test case design process
  Captured in Confluence
  Test team collaborates with design team
Implement automated test script for each test case
Test development in parallel with system development
  Flushes out requirements questions, inconsistencies, and confusions
  Clarifies design
  Uncovers foundational issues early

## Slide 25: The Pipeline
Continuous Integration Pipeline for everything that can be automated
  Static code analysis tools
  Compilation warnings
  Build errors
  “Hello World” integrated tests
  Generation of design package
  Generation of release products
Required before code can be integrated (merged)

## Slide 26: Use Case Based Advancement of System Capability
Working with product owners and relevant stakeholders
  Determine list of operational use cases that can be reasonably developed and demonstrated at this phase of the lifecycle
    Use cases are peer reviewed
    Used for training and familiarization
  Helps to finalize requirements
  Helps to finalize interfaces
Advance hardware in the loop capabilities
  Finalize simulation and emulation capabilities
  Finalize fidelity of hardware environment
Integrated demonstration of capabilities and regular cadence throughout the phase
  We chose a three-month integration cycle
  Based on a two-week team sprint cycle
Continuous Improvement of Tools and Processes
  Enhancing CI pipeline
  Development of emulators and simulators
  Lessons learned from prior phases
  Documenting process enhancements
  Updating templates

## Slide 27: Team Focus: TRR to SAR
Formal Test and Verification

## Slide 28: Automated Testing
Created around Jira/TestRay and Jira API scripting
TestRay allows creation of Test Plans
  Grouping of test cases into test activities
  Plans can be executed in batch
Jira back end communicates with Jenkins server for automated test execution
  Test cycles executed
    Development servers
    Hardware in the Loop Rigs
  Test results pushed back into Jira/TestRay
  Test execution status tracked to completion
    Defects documented

## Slide 29: Across the Lifecycle
Cross Team Integration

## Slide 30: Program Wide Integration Cycles
Gateway is a large program – 11 software development teams (plus sub teams) working initial element launch
  Several larger contractors
  International Partners
  Numerous NASA internal teams
  Test & Verification Labs
  Countless stakeholders
We had to find a way to bring these teams together early and often
  Gateway Software Integration Cycles
    Three month cadence
  Quarterly planning
Essential for driving out interfaces and integrated system operations

## Slide 31: Takeaways

## Slide 32: Closing Thoughts
On any evolving program where change is ongoing, agility is key
  Continual learning is essential
  Continual feedback and process improvement
We have to live within the NPR requirements
  Don’t fight it, try to understand it
    Tailor to what makes sense
  Look for the intent
    Why do we have this artifact or milestone review
  Focus on the “what”, not the “how”
    I have to have requirements, but I don’t need a 300 page Word document