## Slide 1
Aaron Paz, Carbothermal Reduction Demonstration| Annual Program Review | September 10-12, 2024

## Slide 2: CaRD Overview
Needs Addressed by Project | 
Artemis | Advancing ISRU technologies could lead to future production of fuel, water, and/or oxygen from local materials, decreasing supply needs from Earth.
Technology Goals & Objectives | 
Goal #1 | Design, build, and demonstrate performance and efficiency of a prototype solar energy delivery system for a carbothermal reactor.
Objective a. | Demonstrate solar concentrator deployment using prototype avionics and software.
Objective b. | Demonstrate solar tracking using prototype avionics and software.
Objective c. | Collect solar concentrator performance data at Earth operational conditions and using solar flux.
Objective d. | Produce light-weight flight-like concentrator mirrors and integrate them into a deployment and tracking system.
Objective e. | Demonstrate the ability to produce concentrated sunlight at a concentration ratio of ~4000:1 commensurate with the requirements for a carbothermal reactor.
Goal #2 | Integrate solar concentrator, carbothermal reactor, and mass spectrometer to collect Oxygen from Regolith (O2FR) performance and efficiency data.
Objective f. | Collect integrated brassboard performance data under vacuum. Performance data may include thermal management of the reactor and gas analysis accuracy.
Objective g. | Analyze reaction byproducts using a mass spectrometer with hydrogen as the working fluid for carbothermal reaction.
Objective h. | Collect integrated prototype performance data using terrestrial outdoor conditions. Performance data will include optical transmission efficiency and oxygen production efficiency using natural sunlight.
Objective i. | Collect performance data of the partially integrated prototype under vacuum.

## Slide 3: Carbothermal Reduction Demonstration
FY22 | FY23 | FY24 | FY25
TRL
6
5
4
Integrated Brassboard Test
Prototype Vacuum Test
Hydrogen Test
Integrated Prototype Test
Waveguide
Test
KCTE-3 Optical Waveguide/Relay Subsystem
KCTE-4 Gas Analysis Subsystem
KCTE-2 Solar Concentrator Subsystem
KCTE-1 Subscale O2FR Demo
KCTE-5 Solar Concentrator to Optical Waveguide/Relay
KCTE-6 Optical Waveguide/Relay to Reactor
TRL 4: Component and/or breadboard validation in a laboratory environment
TRL 5: Component and/or breadboard validation in relevant environment
TRL 6: System/subsystem model or prototype demonstration in a relevant environment (ground or space)
TRL 7: System protype demonstration in a space environment
KCTE-7 Reactor Fluid System
Notes: Chart purpose: show TRL/SRL/MRL advancement over the project lifecycle schedule. Show TRL advancements as whole integer increases. Show how Key and Controlled milestones align with TRL advancement.
  TRL/SRL/MRL may not advance at each milestone. Often several milestones are required to produce a step increase in TRL/SRL/MRL.
There can be one, or more, of these charts per project as needed.
  For projects with fewer technical elements, the TRL/SRL/MRL data can be combined on one chart.
  For more complex projects, the TRL/SRL/MRL progression can separated into multiple charts by project technical area.
Show TRL, SRL, and MRL data for each technical element on the same chart.
  Delete TRL/SRL/MRL axis-labels that do not apply – e.g., remove SRL/MRL for projects/technical areas where SRL and MRL do not apply.

## Slide 4: CaRD Technical Progress and Results
Worm Gear Drives
Design Complete – Motors Ordered
Lander Mockup
Design Complete, Parts Ordered
Altitude-Azimuth Mount
Design complete
Base
Design complete
Truss Joints with Encoders
Design complete, Encoders Delivered
Optical Shutter
Design Complete

## Slide 5: CaRD Technical Progress and Results
Structural Analysis of Lander Mockup Components
Structural Analysis of Base
Structural Analysis of Carbon Trusses
Electrical Harness Designs Complete

## Slide 6: CaRD Technical Progress and Results
Secondary Mirror
Delivered
Primary Mirror
Delivered
Avionics
4 out of 7 boards complete
Primary Truss
Delivered
Intermediate Truss
Delivered
Secondary Truss
Delivered
Reactor (COPR-Tipping Point)
Completed TVAC Test
Fluid System
Completed TVAC Test
Sun Pointer
Completed

## Slide 7: CaRD Technical Progress and Results
Heliostat Design Complete – Parts Ordered
Flight-Forward Software GUI

## Slide 8: CaRD Transition/Infusion Status
Slide Presented by Jim Reuter at Space Resources Roundtable 2023
CaRD
LIFT-1?
COPR-TP (Sierra Space)
Pilot Plant Concentrator Prototype?
Pilot Plant?
CY23 | CY24 | CY25 | CY26 | CY27 | CY28 | CY29 | CY30 | CY31 | CY32 | CY33
LIFT-1 RFP?
FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33
Pilot Plant Propellant Production?
Pilot Plant Carbothermal?

## Slide 9: CaRD Assessment Summary
Project Name | Performance |  |  |  | Comments
 | C | S | T | P | 
Annual | * |  |  |  | Technical – Successful TVAC test. CDR complete Cost – Heliostat mirror procurement was not accounted for in baseline plan Schedule – On track to complete objectives by March 2025 Programmatic -
 | Oct | Nov | Dec | Jan | Feb | MYR | Apr | May | Jun | Jul | Aug | APR
C |  |  |  |  |  |  |  |  |  |  | * | *
S |  |  |  |  |  |  |  |  |  |  |  | 
T |  |  |  |  |  |  |  |  |  |  |  | 
P |  |  |  |  |  |  |  |  |  |  |  | 
* Change request for heliostat mirror procurement was under review at the time that this presentation was submitted to STRIVES

## Slide 10: Test Plans
Wind Screens
Heliostat
Light Screen
Building 360
(cross section view)
Roll Up Door
Turntable
Operations
Astronaut for Scale
CaRD Prototype

## Slide 11: Key Performance Parameters
1st generation solar-carbothermal system
Reflector Area = 2.3898 m2
635 kg solar concentrator mass
33.4% optical transmission efficiency
1.7 W/kg Delivered Power Density on lunar surface (1080 W/ 635 kg)
CaRD/COPR
Reflector Area = 2.54 m2
193 kg solar concentrator mass
75% optical transmission efficiency
13.5 W/kg Delivered Power Density on lunar surface (2609 W/ 193 kg)
Stowed
Deployed
Solar Thermal Power System for ISRU Applications: Field Deployment and Operation at Mauna Kea (aiaa.org)
2010 Field Demonstration of the Solar Carbothermal Regolith Reduction Process to Produce Oxygen (aiaa.org)

## Slide 12: CaRD Potential Infusion Path
177.165 in
 | Ground Demo (CaRD/COPR) | Flight Demo
Solar Concentrator |  | 
Solar Flux | 800W/m^2 (average for Houston) | 1370 W/m^2 (lunar surface)
Primary Mirror Size | 1.8 m DIA | 1.58m DIA
Delivered Power | ~1000-1300W (weather dependant) | 1300W
Electronics | Avionics - Not Radiation Tolerant | Radiation Tolerant
TVAC | Out of scope | Required
Reactor |  | 
Electronics | COTS | Avionics
TVAC | Complete | 
Fluid Subsystem |  | 
Electronics | COTS | Avionics
Connections | Fittings | Welded
TVAC | Complete | 
Shutter |  | 
Electronics | Avionics - Not Radiation Tolerant | Radiation Tolerant
TVAC | Out of scope | Required
Gas Analysis | COTS | MSOLO
Fluid Interface | Complete | 
Other Cameras | COTS | Flight Qualified
System Vibration | Out of scope | Required
Robotic Arm | Out of scope | Required
Falcon 9 payload fairing diameter 180 inches (4.572 M)
CaRD CAD model scaled with Falcon 9 payload volume represented by blue circles
Image of Griffin lander (image credit: Astrobotic) scaled roughly to match Falcon 9 payload volume
 | CaRD | Griffin Capacity
Mass (kg) | 365 | 625
Power (W) | 182 | 625
Image Credit : Astrobotic