## Slide 1
Matthew Bolcar1 | Alice Liu1 | John Crooke5 | Greg Wenzel8
John Hagopian3 | Tyler Groff1 | Boris Glebov6 | Brian Kern2
Bente Eegholm1 | Alden Jurling1 | Joe Hayden7 | Mark Colavita2
Matthew Bergkoetter1 | Joe Howard1 | Samantha Herath8 | Gary Kuan2
Guangjun Gao1 | Margaret Dominguez1 | Mingjun Li5 | Kaitlyn Summey1
Patricia Lyons4 | Catherine Marx1 | Tim Reichard9 | Nick Collins7
Scott Rohrbach1 | Olha Asmolova1 | Drew Siedel5 | Nick Bond9
The Roman Space Telescope Optical System: Status, Test, and Verification Update
6 July 2026
SPIE Astronomical Telescopes and Instrumentation
14145-27
1Goddard Space Flight Center, 2Jet Propulsion Laboratory, 3Lambda Consulting, 4Peraton, 5Microtel, 6Relative Dynamics, 7Columbus Technologies, 8KBR, 9Adnet Systems,

## Slide 2: Optical System Overview

## Slide 3: Observatory Expanded View
SCIPA = Spacecraft Bus + Integrated Payload Assembly
Spacecraft Bus
Integrated Payload
Assembly (IPA)
Spacecraft Bus Avionics Panels
Propulsion Module
Communications
Module
Wide Field
Instrument (WFI) Cold Sensing Module
Coronagraph
Instrument (CGI)
(outer enclosure
not shown)
Instrument Carrier (IC)
Imaging Optics Assembly (IOA)
Deployable Aperture Cover (DAC)
Outer Barrel
Assembly (OBA)
Solar Array Sun Shield (SASS)
OSD (OBA/SASS/DAC)
SCIPA
Observatory = SCIPA + OBA/SASS/DAC
Observatory

## Slide 4: Optical Block Diagram
AOM = Aft Optics Module
ACM = Alignment Compensation Mechanism
CGI = Coronagraph Instrument
CSM = Cold Sensing Module
DM = Deformable Mirror
DOF = Degree of Freedom
EWA = Element Wheel Assembly
EXCAM = Exoplanet Camera
FCM = Focus Control Mechanism
F1/F2 = Fold Mirror 1/2
FOA = Forward Optics Assembly
FPAM = Focal Plane Alignment Mechanism
FSM = Fast Steering Mirror
HLC = Hybrid Lyot Coronagraph
IWA = Inner Working Angle
LOCAM = Low Order Wavefront Sensing Camera
MPA = Mosaic Plate Assembly
OTA = Optical Telescope Assembly
OWA = Outer Working Angle
PMA = Primary Mirror Assembly
RCS = Relative Calibration System
SMA = Secondary Mirror Assembly
SPC = Shaped Pupil Coronagraph
TCA = Tertiary Collimator Assembly
TM = Tertiary Mirror
WFI = Wide Field Instrument

## Slide 5: Optical Path
TCA
AOM
CGI
WFI
WIM: Filter (8x)
FPA
WSM: Prism
FPA
WSM: Grism
FPA

## Slide 6: Flight Optical Compensators
Compensator | Optical Degree of Freedom
SM Focus Drives (FD)* | Defocus
SM Alignment Drives (AD)* | Decenter (x)
 | Decenter (y)
 | Defocus
 | Tip
 | Tilt
AOM Fold Mirror 1 (FM1) | Defocus
 | Tip
 | Tilt
WFI Alignment Compensation Mechanism (ACM)† | Defocus
 | Tip
 | Tilt
TCA Tip/Tilt Fold (TTF) | Tip
 | Tilt
Compensate Wavefront Error (WFE)
Common to Each Channel
Compensate Focus WFI Channel
Compensate Pupil Shear in CGI Channel
*Heritage actuators from previous program
†Heritage JWST actuators

## Slide 7: Optical Verification Overview

## Slide 8: Optical Alignment & Verification Summary
Component Level
Element Level
Assembly Level
Observatory Level
Instrument Carrier TVAC Photogrammetry Test
IC Simulator given to WFI and CGI to place latches and check alignment
Instrument WFE & Alignment verification testing performed on GSE Interface
Spacecraft Bus + IPA (SCIPA)
WFI pupil shear/clocking verification & vignetting check with LED system @TVAC
CGI pupil shear/clocking verification with FSA fibers @TVAC
WFI focal surface verification & wavefront x-check with sub-ap FDPR @TVAC
Primary Mirror Offner Null & Airbag in Ambient
Multipoint Support + CGH @ Amb. & 265K
Primary Mirror Assembly
Gravity Offloaded, CGH @265K
1g CGH @ 265K
0g cross-check horizontal multi-orientation @ Ambient
IOA Pre-vibe
Ambient soft-vac with gravity offload; I/F both channels FDPR in WFI; SHWFS in CGI w/ and w/o gravity offload
Observatory Pre-/Post-vibe ambient vignetting with SAVI
Analysis of 0g on-orbit performance
Instrument Carrier
IOA
IPA / SCIPA
Observatory
Science Instruments
IOA Post-vibe
Ambient & cold hard-vac, 1g. FDPR in WFI; SHWFS in CGI.
Integrated Payload Assembly (IPA)
Post-integration rigid-body metrology (IOA, CGI, WFI)
Ambient pupil alignment check with FSA fibers (CGI only)
CGH = Computer Generated Hologram
FDPR = Focus Diverse Phase Retrieval
FSA = Forward Structure Assembly
GSE = Ground Support Equipment
I/F = Interferometry
SAVI = System for Alignment and Vignetting Inspection
SHWFS = Shack-Hartmann Wavefront Sensing

## Slide 9: I&T Flow with Metrology & Optical Test Activities
SCIPA Checkout & Pre-Env Powered Tests
SCIPA EMI/EMC 1
Integrate IPA to SC Bus
OBS Vibe, Acoustics, and Shock
Post-Env. Deployment
SCIPA TVAC
OBS Pre-Env. Powered Testing
SAVI Test
Prep for Shipment / Ship
OSD to SCIPA
Integration
Stow / Final closeouts
OBS Post-Env. Powered Testing
Pre-Env. Deployment Testing
SCIPA EMI/EMC 2
SCIPA Vibe
Integrate IPA
CGI Delivered
WFI Delivered
OTA Checkout
IC Available
OTA Delivered
Launch Site Processing
Launch!!
SCIPA TVAC Pathfinder Test
SCIPA Powered Tests
WFI Checkout
CGI Checkout
Post-Env Powered Tests
Configure SCIPA for Obs I&T
Final PM Inspection and Cleaning / SAVI Test
IPA
SC / IPA
Observatory
We Are Here
Rigid-body Metrology
Pupil Alignment Check
System for Alignment and Vignetting Inspection (SAVI)
Stray Light Inspection / Test
Optical Verification Testing

## Slide 10: SCIPA TVAC Optical Test

## Slide 11: Test Objectives
Verify CGI & WFI alignment to the OTA
  Verify instrument pupil alignment in shear and clocking degrees of freedom
  Verify WFI focal plane placement relative to the OTA focal surface
Demonstrate no vignetting in the WFI channel
Cross-check end-to-end system wavefront error in the WFI channel
Demonstrate wavefront sensing & control operations
Characterize wavefront error and alignment sensitivity to changes in Spacecraft temperature
Other tests of opportunity (test goals)
  Wavefront stability model validation test using Focus Diverse Phase Retrieval (FDPR)
  Secondary mirror kinematics calibration test
  Compare observed thermal background to model predictions
  Compare stray light measurements to model predictions

## Slide 12: SCIPA TVAC – Optical Test Configuration
USF (Upper Support Frame) supporting OLAFS, 6x Photogrammetry (PG) cameras, PG “pogo stick” targets & vibration isolation system
OLAFS (Optical Large Aperture Flat System) – 1.8 m mirror with Tip/Tilt actuators.
Top Deck Assembly w/ LED System
6x Forward Structure Assembly (FSA) “Diving Boards” hold fiber sources above the primary mirror

## Slide 13: As-Run Optical Tests
PG System Alignment Measurement
Configure OTA at nom. alignment
CGI Pupil Alignment
CGI ExCam Gain
Ambient Temp/Press.
Dryout, HC1, CC1, HC2, CSB
PG System Setpoint Check
OLAFS Checkout / PR-049
TPT IFE Part 1
OLAFS Checkout / PR-049 fixed
TPT IFE Part 2
LED Ring Alignment & PG Check
WFI Find Best Focus
Configure OTA at nom. alignment
CGI Pupil Alignment
Cold Thermal Cycle 2
ACM Compen-sation
WFI Find Best Focus / IFE Part 3
SM Offset for Gravity Sag
CGI Pupil Alignment
Cold Op Balance
PG System Alignment Measurement
CGI Pupil Alignment (w/OLAFS move)
WFI Pupil LED Test (24 prime LEDs)
WFI FDPR “Short”
Analysis Hold
Set Compen-sators
Other Tests (e.g., ACS Guide Star Phasing (SYS-40))
WFI Pupil LED Test (vignetting LEDs)
SM Kinematics Test
WFI-OLAFS-CGI Weak Lens Imaging
Thermal Cold Op. Tests
PG System Alignment Measurement
CGI Pupil Alignment
WFI Pupil LED Test
WFI FDPR “Long”
Cold Op Balance
Transition Monitor
COBHOB
Hot Op Balance
WFI FDPR “Very Short”
Set Compen-sators (Take 2)
WFI FDPR “Very Short”
LED Ring Alignment & PG Check
WFI Pupil LED Test
WFI FDPR “Short”
PG System Alignment Measurement
CGI Pupil Alignment
Ambient Temp/Vacuum
Hot Op Balance
CGI Pupil Alignment (w/LOCAM)
Thermal Hot Op. Tests & Functional
SM Kinematics Investigation
ACM ROM (includes CGI & WFI data collects)
(MRT-13d) Set Compen-sators
TCS-17 (AMS Setpoint w/FD test)
Configure OTA at nom. alignment
CGI Pupil Alignment
Configure OTA to launch
Notes: 65 days, 24/7 operations,

## Slide 14: Example WFE Trending – Model-subtracted Residual
F6SCA17CE, Fiber 6, F158, 1550 nm
Initial compensation using ACM Dz based on Find Best Focus sweep to reduce overall defocus ahead of main test campaign
  Due to model errors at the time, our correction was wrong and system focus actually got worse
Second compensation following first ColdOp Balance used improved optical model and implemented with both SM & ACM
  System performance substantially improved
Final compensation exercised all degrees of freedom and targeted a joint filter and Prism optimal wavefront to demonstrate controllability and achieve final cross-check criteria
 60 nm Cross-check Requirement
ACM & SM Compensation
ACM & SM Compensation
ACM Compensation

## Slide 15: WFI Pupil Alignment – LED Test Description
A ring of LEDs are position within the clear aperture:
LEDs are turned on individually. Each LED floods the WFI field.
OTA structure blocks part of the LED ray bundle
The entrance aperture plate further limits the field-of-view
In the WFI pupil, the same ray bundle can also be clipped by features in the pupil mask
The features in the OTA and the WFI pupil cast shadows that are imaged at the WFI detector
Positions of shadows on the WFI detector are related to the as built positions of the OTA and the WFI pupil mask to determine their relative alignment
1
2
3
4
5
1
2
3
4
5
LEDs
OTA

## Slide 16: Example WFI Pupil Alignment Measurement
0
1
Note: Data from SCA8 missing due to temporary readout issue.
Test Measurements Match Predictions

## Slide 17: Example WFI Pupil Alignment Prediction
0
1
Test Measurements Match Predictions

## Slide 18: WFI Vignetting Test
Obstructions caused by FSA fibers observed at 4 of 6 FMS diving boards.
Projecting LED images onto IOA entrance pupil shows locations of fibers (left)
  Fibers observed in the same locations in inspection photos (right)
  Following slides show details of each fiber
Remaining 2 fibers likely pass through coverage gaps between LED modules

## Slide 19: CGI Pupil Alignment Trending
Pupil Shear (raw)
TVAC
SES
SSDIF
TVAC
SES
SSDIF
CGI pupil alignment data shows expected behavior across multiple environments
  Early cleanroom measurements are consistent considering commanded tip/tilt fold mirror poses to test sensitivity
  TVAC data all very consistent across thermal plateaus
    Hot plateau shear outlier is because we commanded TTF to place the pupil at a specific ExCam location
    Cold plateau clocking outlier due to incorrect DM setting
X
Y
Clocking

## Slide 20: System for Alignment and Vignetting Inspection (SAVI)

## Slide 21: System for Alignment and Vignetting Inspection (SAVI)
SAVI is a test that was developed to address the lack of optical performance testing (aside from metrology) at the Observatory level
It is a low-budget, ambient test to cross-check the optical alignment and verify no vignetting of the optical path following Observatory environmental testing
  Bonus: the test could also inspect coating integrity of the PM and SM
The SAVI test uses a digital camera with a 300-800 mm zoom lens to “look back” through the optical path

## Slide 22: Example Details Seen with SAVI
WFI channel shown to the right
  Focusing on the entrance aperture plate with the blue reflection from the F062 filter
  Notice the individual SCA’s
  The reflection back from the fiber tips very easy to see
The CGI channel shown to the left
  We did not explicitly “look into” CGI for this test due to complexity of optical path and intervening masks

## Slide 23: SAVI Vignetting Check
SAVI moved along the PM perimeter
Photos were acquired with the PM edge visible, focusing first on the edge, then at infinity (detector) from the same physical SAVI position
  Example images shown to the right.
None of the images indicated any vignetting
Right side of PM:
Focusing on edge,
then on filter/detector
Top of PM:
Focusing on edge,
then on filter/detector
Positions of the selected image examples shown to the right

## Slide 24: SAVI Pupil Alignment Check
For a given SAVI camera pose (as measured by external metrology):
  Image the SM support tube scraper
  Image the filter mask strut
  Compare the relative positions in the images to model predictions (see right)
Repeat process before and after Observatory environmental testing
  Look for changes in relative positions before and after vibe & acoustic testing
Measurement uncertainty on par with verification testing done during SCIPA TVAC
  Though SAVI is an ambient test and does not capture cooldown effects

## Slide 25: Summary and Conclusion
The Roman Space Telescope optical system has completed a comprehensive test verification program
  Ambient rigid body metrology and stray light inspections throughout integration & test
  Thermal vacuum optical alignment and wavefront error performance verification
  Optical alignment and vignetting cross-checks through Observatory-level environmental testing
All optical performance requirements have been verified with significant margin
Roman is currently completing launch site processing and integration to the launch vehicle for an August 30 launch readiness date!

## Slide 26: Backup