## Slide 1
GO / SPACE TRANSPORTATION
ANNUAL REVIEW
Eric Pencil, GRC
EP PORTFOLIO MANAGER
AUGUST 26, 2026
Advanced Electric Propulsion (EP) Portfolio
nasa.gov | Space Transportation – GO Domain
Tom Liu, GRC
AMPERE TECHNICAL LEAD
Jason Frieman, GRC
AMPERE TECHNICAL LEAD
Gabriel Benavides, GRC
SSEP TECHNICAL LEAD
Vernon Chaplin, JPL
DEEP SPACE TASK MASTER
John Yim, GRC
JANUS TECHNICAL LEAD
George Williams, GRC
SONET PROJECT MANAGER
Rob Thomas, GRC
ADVNEXT TECHNICAL LEAD
Lindsay MacLeod, GRC/CGI
EP PROJECT INTEGRATION LEAD

## Slide 2
Flagship Advanced EP Projects
Other Advanced EP Projects/Activities
GO / Space Transportation Annual Review
Advancing electric propulsion system technologies for low-power and mid-power NASA applications
Technologies include low-power and mid-power hall effect thrusters (HETs), power processing units (PPUs), and feed systems.
Collaborations designed to develop low-to-mid-power applied field MPD thrusters, low-power krypton hall thruster, and advanced manufacturing techniques for the 12kW design.
Portfolio Manager | Eric Pencil, GRC
Budget Analysts | Larissa Fisher, GRC / Ben Bauman, GRC
Scheduler | Mike Erlenbach, GRC
Project Integration | Lindsay MacLeod, GRC
Advanced Electric Propulsion (EP) | FY26 Portfolio Snapshot
Advanced EP Objectives
Executing Phase 1 formulation activities on schedule and on budget to successfully position the project for execution across its three strategic pillars: Krypton Pathfinder, Industry Challenge, & Stakeholder Consortium
AMPERE
SpaceX rocket successfully carried Northrop Grumman’s MRV MEP mission to space, which uses NASA Glenn’s electric propulsion technology to extend commercial satellite lifetimes
SSEP
RFI for commercial gimbals closed in July with excellent industry response; more than half of the 11 vendors that responded were previously unknown to the NASA propulsion team
Deep Space
Supported PDR for HEU 1 kWe reactor (KRUSTY-derivative) integrated on a ESPAStar spacecraft (Colossus)
JETSON / SONET
Successfully worked with Colorado State University to demonstrate N2 LIF on 8 kW class thruster
40+ doctoral and masters students being trained in advanced space power and propulsion
USSF SSTI SPAR
Demonstrated stable thruster operation with 40% increase in thrust-to-power ratio
Completed fabrication and functional testing of AdvNEXT prototype PPU
USSF AdvNEXT
Completed Large Vacuum facility design study, a conceptual design of a "Benchmark Reference Vacuum Facility” that meets all JANUS requirements while operating minimum EP system subset
JANUS Study
Announcements of Collaboration Opportunities (ACOs)
Hyperion
Busek
Rocketdyne
Entered Project Closure Phase in FY26
New in FY26
Commenced pre-FY26, continuing through FY27
Kicked off three new ACOs in late FY26

## Slide 3
GO / Space Transportation Annual Review
Collaborative NASA-industry development of domestic commercial capability to meet end-user needs, including:
Commercial: GEO communications, LEO/MEO constellations, satellite deployment and servicing, large orbital platforms
Military: Dynamic maneuvering in contested environments, Golden Dome
NASA: Deep space exploration and science, cis-lunar / cis-Martian logistics, nuclear electric propulsion
Right solution. Right market. Right now.
Leveraging past R&D and commercialization lessons to catalyze domestic and cost-effective mid-power Hall Effect Thruster (HET) development
Develop a mid-power HET design to enable a domestic commercial product that is cost-effective for industry and capable enough for NASA
Target an individual thruster recurring expense (inclusive of manufacturing and acceptance) of <$500k
Target thruster qualification in ≤5 years to enter mid-power HET market
Identify risks and plan mitigations addressing other elements of a complete mid-power HET propulsion system
Domestic 5-kW-class HET for commercial and deep space missions, leveraging:
Leveraging NASA technologies to deliver the performance and life with the robustness and reliability demanded by end-users
Commercial production expertise to drive down unit costs with repeatable and manufacturable designs
Krypton optimization to enable 20-30x propellant cost reductions without sacrificing performance, life, or xenon compatibility
Reliable. Affordable. Capable.
Kr Pathfinder Conceptual Design Review | Week of 09/22/26
Phase 1 Final Report | 09/30/26
AMPERE Phase 2 Industry Day | 10/20/26
Thruster Challenge Released | Late 10/2026
Inaugural Consortium Meeting | 12/2026
Krypton Pathfinder Test Readiness Review | 02/2027
Project Sponsor | GO / Space Transportation
Project Manager | Eric Pencil, GRC
Lead Engineers | Thomas Liu, GRC / Jason Frieman, GRC
JPL Lead | Lee Johnson, JPL
Budget Analyst | Larissa Fisher, GRC
AMPERE | Project Snapshot
Project Objectives
Technology Description
Transition / Infusion Plans
Upcoming Milestones
Krypton (Kr) Pathfinder
Industry Partnership
Stakeholder Consortium
Project Elements
Advanced Mid-Power Electric Rocket (AMPERE)
Significant FY26 collaborative investments demonstrate AMPERE’s broad appeal to stakeholders
CoECI: Secured cost-share to execute both the subsystem market analysis and thruster prototyping challenges
STRG ESI: Proposed STMD GO Domain’s top-rated Catalyst solicitation topic for a university partnership to conduct critical research into krypton life-limiting mechanisms
NASA GRC: Selected for a GRC High-Priority Investment grant to procure advanced optical diagnostics (Laser Induced Fluorescence) essential for mitigating thruster lifetime risks
Department of War (DoW): Initiated cost-sharing and value-added discussions with DoW for the stakeholder consortium and post-FY27 roadmap activities (e.g., FSAA and ACO)
Partnerships / Collaborations

## Slide 4
AMPERE | Project Elements (FY26-27)
Advanced Mid-Power Electric Rocket (AMPERE)
GO / Space Transportation Annual Review
NASA Technology
Commercial Partner
Krypton
Total Cost
Reliability
Performance
What Stakeholders Require:
High reliability and robustness
Low total cost burden
Sufficient performance for mission capture
Philosophy
Industry Challenge
Stakeholder Consortium
Kr Pathfinder
Opportunistic Kr risk-reduction testing at GRC
NASA technology improved Kr lifetime by 5x relative to SoA
Provides existence proof that domestic industry can produce a mid-power HET for <$500k
Provides existence proof that a domestic mid-power electric propulsion ecosystem can be sustained
Provides existence proof that NASA technology can result in mid-power Kr HET with comparable capability as SOA Xe HET

## Slide 5
AMPERE | FY26 Accomplishments
Advanced Mid-Power Electric Rocket (AMPERE)
GO / Space Transportation Annual Review
Trade Study Process
Market Survey Participants
Krypton Pathfinder Thruster Assembly Model (left) and Flow Analysis (right)
DEFINING THE NEED
Krypton Pathfinder
Proven Breakthroughs: Conducted opportunistic risk-reduction testing, demonstrating breakthrough krypton performance and life using proven NASA technologies
Rapid Maturation: Advanced pathfinder thruster from concept to detailed design in ~6 months, backed by high-fidelity modeling & simulations
Forward Momentum: Initiated long-lead procurement and fabrication to enable February 2027 test readiness
PROVING
THE TECHNOLOGY
PROVING THE PARTNER
PROVING THE MARKET
Project Formulation
Market-Aligned Strategy: Surveyed 20+ stakeholders (end-users, providers, government) to pinpoint user needs and industrial base gaps
Requirement Derivation: Translated end-user needs into specifications that balance reliability, robustness, and cost via NASA heritage technology, commercial manufacturing expertise, and krypton optimization
Stakeholder-Driven Design: Executed rigorous trade studies to define key thruster attributes needed to meet end-user needs
DEFINING
THE NEED
Industry Challenge
Innovative Approach: Secured FY26 STMD CoECI funding as NASA’s inaugural Technology Maturation Prize, expected to be launched in October 2026
Industry Activation: Initiated competitive challenges designed to accelerate mid-power thruster hardware development and define the supporting subsystem market
PROVING
THE PARTNER
Stakeholder Consortium
Strategic Alignment: Architected and initiated a collaborative consortium model to stimulate the market and ensure continuous stakeholder alignment with member onboarding expected in October 2026
PROVING
THE MARKET

## Slide 6
Risk / Issue | Mitigation Approach | Impact
FY26 Government Shutdown 43-day impact to project schedule baseline due to lapse of government funding at the start of FY26 | Replanned project formulation activities Transitioned from a waterfall to spiral development model Parallelized stakeholder discussions with technical trade studies / design | Completed all formulation activities per original budget and schedule
Phase 2 Commercial Partnership Approach Industry concerns about impacts of past NASA EP partnership approaches on competitive landscape | Engaged EP providers in open dialogue regarding past NASA partnerships Assessed innovative procurement / collaborative approaches to address industry concerns Iterated upon AMPERE partnership approach per stakeholder feedback | Formulated innovative commercial partnership approach with stakeholder buy-in
Project Thruster Focus Directed project scope was primarily limited to the thruster rather than the entire propulsion system | Assessed initial gaps via direct stakeholder dialogue Initiated CoECI-funded system market landscape survey Conducted environmental qualification risk-reduction activities on candidate PPU hardware | Developed means to evaluate system gaps and recommendations for future investment
Krypton Performance and Lifetime SoA thrusters have demonstrated undesirable performance and life with krypton propellant | Supported krypton risk-reduction testing of key NASA technologies Anchored initial krypton propellant modeling and simulations against acquired data Infused key findings into AMPERE pathfinder design | Reduced technical risk associated with krypton performance and life
AMPERE | FY26 Issues / Risks
Advanced Mid-Power Electric Rocket (AMPERE)
GO / Space Transportation Annual Review

## Slide 7
AMPERE | FY26 Conclusion
Advanced Mid-Power Electric Rocket (AMPERE)
GO / Space Transportation Annual Review
AMPERE: Reliable, Affordable, Capable. Ready to Proceed.
Executing Phase 1 formulation activities on schedule and on budget to successfully position the project for execution across its three strategic pillars:
Poised to demonstrate existence proofs for the AMPERE technology, industry partner, and market in FY27
  Krypton Pathfinder (Technical Readiness)
  Reduced technical risks by demonstrating breakthrough krypton performance and life while rapidly maturing a detailed thruster design
  Industry Challenge
  (Agile Acquisition)
  Secured investments to pursue innovative procurement models, including industry competitions to accelerate domestic thruster prototyping
  Stakeholder Consortium
  (Market Alignment)
  Completed a thruster-centric market survey to identify end-user needs, initiated a CoECI-funded system-centric market landscape analysis, and architected a collaborative framework to stimulate and sustain the mid-power EP ecosystem

## Slide 8
GO / Space Transportation Annual Review
Potential Users: U.S. commercial Hall Effect Thruster (HET) providers and end-users
Potential Missions: NASA missions
Potential Applications: Spacecraft maneuvering
Product Service Lines: First mission—Northrop Grumman MEP (launched July 2026)
Patent / Licensing status: 14 evaluation licenses executed; 4 transitioned to commercial licenses; 3 awarded patents, 1 provisional patent
  Over 400 GB of data generated (e.g., test data, CAD models, drawings, procedures, etc.)
Advancing sub-kilowatt EP technologies for small spacecraft, licensing them to U.S. industry, and demonstrating their reliability through integrated engineering models suitable for lunar, Martian, and deep space missions.
Strengthen the domestic small spacecraft EP industrial base and lower cost of EP
Disseminate knowledge using one embodiment of the SSEP technology (H71M) while supporting industry’s own embodiments to address a spectrum of needs
Partner with US industry to identify and solve the most widespread sub-kW EP design, test, and manufacturing challenges
Patent new technologies and processes to ensure availability to the US industrial base
Disseminate knowledge through licensing, SAAs, data agreements, and open literature
Provide training to industry partners on design and processes
NASA is developing a suite of sub-kW electric propulsion (EP) technologies, which are being successfully licensed to U.S. industry through non-exclusive, no-cost agreements.
The technologies are being demonstrated with the fabrication of an engineering model integrated system (thruster, PPU, and flow controller), which provides our commercial partners with the documentation necessary to reliably produce an initial embodiment.
This embodiment is appropriate for small spacecraft (200-500 kg s/c) missions to the moon, Mars, or beyond.
Complete Integrated System Test Campaign and Data Analysis | 11/20/26
Completion of EM/flight-like thruster | 11/20/26
Complete combined test of thermal, wear, and plume characterization | 01/31/27
Complete PPU TVAC Testing | 05/21/27
Project Sponsor | GO / Space Transportation
Project Manager | Eric Pencil (GRC-MT)
Lead Engineer | Gabriel Benavides (GRC-LTS)
Budget Analyst | Larissa Fisher (GRC-BRP)
SSEP | Project Snapshot
Project Objectives
Technology Description
Transition / Infusion Plans
Upcoming Project Milestones
Small Spacecraft Electric Propulsion (SSEP)

## Slide 9
EM AUX Board
SSEP | FY26 Highlights / Accomplishments
Small Spacecraft Electric Propulsion (SSEP)
GO / Space Transportation Annual Review
EM DCIU Board
NASA and NG Team Photo After Completion of Flight Acceptance Testing
  Fabrication & Testing of EM Propellant Flow Control Panel – Complete
The EM thruster design is ~95% complete and fabrication ~50% complete
Finalization of the design pending completion of a couple remaining structural modeling investigations to ensure key structural components meet launch environment requirements before cutting metal on the remaining assemblies
Most components have rough drawings prepared pending any final minor design modifications
Thruster fabrication on track to meet FY27 test schedule.
Transferred magnetic circuit design data to licensee HiFunda, LLC, which seeks to be a component supplier
  Design & Fabrication of EM Thruster – Nearly Complete
Completed design and fabrication of all engineering model (EM) power processing unit (PPU) board assemblies, custom magnetics, enclosure hardware, and harnessing
Functional and performance verifications were successfully completed on each PPU board (i.e., Discharge Supply, Auxiliary Supply, and Digital Control and Interface Unit)
Now performing preparing for integrated system testing with EM thruster and EM propellant flow controller
  Significant progress transferring the PPU design to licensee Frontier Electronic Systems
  Design & Fabrication of EM PPU – Complete
SpaceX rocket launched three Northrop Grumman Mission Extension Pods (MEPs), each equipped with NASA’s SSEP electric propulsion technology to extend the lifetimes of commercial satellites in geosynchronous orbit
Each MEP attaches to a satellite running low on propellant and, using a pair of NASA‑licensed miniaturized thrusters, takes over responsibility for maintaining the spacecrafts station and attitude control
This added propulsion allows the aging satellites to operate for at least six additional years instead of being retired
  July 2026 SpaceX Rocket Launch

## Slide 10
SSEP | FY26 Issues / Risks
No current technical issues identified
Technology development is currently on track to meet all project goals / design requirements
Most FY26 execution challenges were driven by outside forces:
Small Spacecraft Electric Propulsion (SSEP)
GO / Space Transportation Annual Review
  Issue: Significant changes to P-card procurement process at GRC has created bottleneck for routine procurements
    P-card group has reported backlog of hundreds of orders from across the Center
    Procurements that historically took a few days to process are now taking weeks (in some cases, months)
  Impact: Procurement process has resulted in periodic schedule slips
  Mitigation / Risk: While we work to limit impact by planning well in advance, unless P-card procurement process efficiency improves, risk remains that further procurement-related schedule slip can occur
  Issue: SSEP project draws on key subject matter experts at GRC who also have duties on conflicting higher priority / visibility projects
  Impact: This results in recurring limitations on availability of key research and facility personnel
  Mitigation / Risk: While we coordinate needs carefully with other projects, the critical need of other projects has and will continue to periodically result in SSEP schedule slip
  Government Shutdown
  Issue: GRC’s B301 liquid nitrogen system upgrade is preventing our ability to use the facility for testing
  Impact: This is delaying our integrated thruster test
    Current estimate for test facility readiness is now 10/13/26
    Now anticipating execution of integrated system test in November, rather than September
  Mitigation / Risk: We will merge the integrated system test with more extensive performance testing that was planned for Q1 FY27 to pull back much of the schedule slip
  P-Card Procurement Process
  Personnel Limitations
  Issue: October-November 2025 government shutdown halted work needed to meet critical project deadlines
  Impact: This created a significant operational backlog and schedule slippage
  Mitigation / Risk: While we plan and prepare for the possibility of another government shutdown in CY26, the risk remains that another schedule slip will occur in that event
  Facility Upgrades

## Slide 11
Assess options for developing or procuring low-cost gimbal suitable for both MaSMi and GRC-developed NASA-H71M thruster
Assess readiness of ExoTerra’s current PPU design to meet NASA mission requirements
Test MaSMi thruster with 1 kW PPU developed at NASA GRC
Demonstrate operation of MaSMi thruster with a high-reliability XFS developed by CU Aerospace
Test gimbal prototype with the MaSMi and NASA-H71M thrusters
Oversee updates to ExoTerra’s PPU design to allow it to control the CU Aerospace XFS
Initiating the development and qualification of a full EP system built around the Magnetically Shielded Miniature (MaSMi) Hall thruster to enable small satellite missions to diverse planetary targets
Project Sponsor | GO / Space Transportation
Pre-Formulation Lead | Eric Pencil, GRC
Budget Analyst | Larissa Fisher, GRC
Technical Team Vernon Chaplin (JPL, task manager), Rich Hofer (JPL, thruster), Brandon Wang (JPL, PPU), Mike Johnson (JPL, gimbal), Gabriel Benavides (GRC, thruster), Corey Rhodes (GRC, PPU) | 
GO / Space Transportation Annual Review
NASA-funded work in FY26-FY27 to initiate development and qualification of a full EP system built around MaSMi with a system cost and risk posture appropriate for SIMPLEx missions (Class D)
Available power processing units (PPU), xenon feed systems (XFS), and gimbals are currently less mature than the thruster itself; goal is to finalize system design choices and complete necessary NRE to prepare the EP system for inclusion on high cost-constrained mission proposals.
Smallsat (<300 kg) missions to Venus, Earth’s moon, asteroids, gas giants, and outer planets can be enabled by high-performing, high-throughput kW-class Hall thruster
MaSMi Hall thruster design was based on technical breakthroughs from development of higher power Hall thrusters such as HERMeS/AEPS and guided by high-fidelity plasma modeling with the Hall2De code
Following qualification at JPL, thruster design was licensed to ExoTerra and Apex for commercial production; ExoTerra is delivering kW-class electric propulsion flight systems, and Apex is using vertical integration to manufacture satellite buses at high volume and speed.
Deep Space Study | Project Snapshot
Project Objectives
Technology Description
Task Plan Overview
Deep Space Electric Propulsion Study: Low Power Electric Propulsion System Using MaSMi Hall Thruster
ExoTerra on contract for PPU study | 9/15/26
Test GRC keeper PS with MaSMi cathode | 10/15/26
Test full MaSMi thruster with GRC PPU | 11/15/26
Test CU Aerospace XFS with MaSMi | 12/15/26
Upcoming Milestones
Notes: Task Plan Overview Details:
Assess options for developing or procuring low-cost gimbal suitable for both MaSMi and GRC-developed NASA-H71M thruster
  Most NASA mission applications of EP require a gimbal for thrust vector control during primary firings and for spacecraft attitude management and momentum unloading.
Assess readiness of ExoTerra’s current PPU design to meet NASA mission requirements
  Up-front identification of any changes needed to electronic parts or other design features will significantly reduce cost and schedule risk for future missions proposing to use this PPU.
Test MaSMi thruster with 1 kW PPU developed at NASA GRC
  Demonstrating operation of MaSMi with an updated version of NASA GRC's in-house PPU will provide system configuration flexibility for programmatic risk reduction.
Demonstrate operation of MaSMi thruster with a high-reliability XFS developed by CU Aerospace
  This XFS was designed for MaSMi and has a redundant valve configuration preferred for NASA missions; this project will test the XFS and thruster together for the first time.
Test gimbal prototype with the MaSMi and NASA-H71M thrusters
  Identifying a technically viable gimbal with acceptable size and cost is an important step for mission proposal readiness.
Oversee updates to ExoTerra’s PPU design to allow it to control the CU Aerospace XFS
  ExoTerra's PPU can be updated to run the CUA XFS without requiring re-qualification of its most complex parts (the anode discharge circuit and keeper ignition circuit).

## Slide 12
Deep Space Study | FY26 Review
Reviewed available gimbals and identified several viable options for MaSMi and the NASA-H71M Hall thruster
NASA-H71M is a 1 kW-class thruster developed at NASA GRC. Ensuring cross-compatibility of the selected gimbal with both Hall thrusters maximizes the benefits of this development work for NASA and retains flexibility for future mission proposals led by JPL and other NASA centers.
A JPL-developed gimbal design was reviewed in detail, identifying some minor gaps to close in the structural analysis and part selections that may need to be revised.
A Request for Information (RFI) for commercial gimbals was released in May 2026 through direct communication with identified vendor candidates and public posting on SAM.gov, specifying preliminary quantity requirements, technical specifications, design details, qualification test history, interface requirements, and delivery cost/schedule estimates for gimbal options.
The industry response to the gimbal RFI was excellent, with 11 vendors submitting detailed responses. More than half of these respondents were previously not known by the NASA propulsion team as candidate Hall thruster gimbal vendors.
Deep Space Electric Propulsion Study: Low Power Electric Propulsion System Using MaSMi Hall Thruster
GO / Space Transportation Annual Review
Examples of Commercial Gimbal Options for 1 kW Hall Thrusters
Propel Space EP2M-5
(image from propelspace.com)
Beyond Gravity APPMAX2-XS
(image from beyondgravity.com)
Worked toward an SBIR contract with ExoTerra to enable PPU design review by JPL and design updates for compatibility with the CU Aerospace XFC
Drafted Scope of Work and Justification for Phase III documents to support the contract
ExoTerra submitted proposal; NASA SBIR contracting paperwork is in progress as of August 2026
Supported design updates to GRC's PPU and prepared for test with MaSMi
JPL shared MaSMi electrical interface requirements and startup and oscillation data with GRC
GRC's updated engineering model PPU design was sent out for fabrication in July 2026
FY26 Accomplishments

## Slide 13
Deep Space Study | FY26 Review
Deep Space Electric Propulsion Study: Low Power Electric Propulsion System Using MaSMi Hall Thruster
GO / Space Transportation Annual Review
Potential Users: NASA, DoW, commercial satellite bus vendors
Potential Missions: JPL/NASA, DoW, and commercial smallsat missions requiring high spacecraft Δv
Potential Applications: Primary propulsion for smallsat missions enabling higher delivered mass, launch window flexibilty, elimination of critical events such as orbit insertion, and complex trajectories such as multi-body rendezvous
Transition / Infusion Plans
Schedule slips in FY26 caused by:
  Congress did not reauthorize SBIR program until halfway through FY26, delaying start of PPU work with ExoTerra
  Limited personnel availability due to other NASA project commitments caused some testing tasks to be pushed from FY26 to early FY27
Currently available funding for ExoTerra Phase III SBIR contract will be sufficient for them to complete design updates but not deliver hardware; additional Year 3 funding of ~$500k is needed for engineering model PPU build at ExoTerra and testing with MaSMi thruster at JPL
FY26 Issues/Risks
The MaSMi thruster was originally developed with JPL internal R&TD funding, while NASA-H71M and the NASA 1 kW PPU were developed independently at NASA GRC. This project represents a new level of collaboration between GRC and JPL on electric propulsion for smallsats, supported by NASA STMD.
  Expected outcome of this work will be multiple EP system configuration options that reduce cost and risk for upcoming NASA mission proposals
The SBIR contract to further prepare ExoTerra's PPU for use with MaSMi on NASA mission applications will extend a collaboration between JPL and ExoTerra that began with:
  ExoTerra's licensing of the thruster design from JPL in 2020
  JPL's support of ExoTerra's thruster qualification and initial flight unit builds through a NASA Space Act Agreement in 2022 – present
Partnerships/Collaborations
Schematic of CU Aerospace's CAMFLOW XFS, from IEPC-2022-590

## Slide 14
This FY26 Review reflects NASA’s support of the SONET team, and in no way reflects​ the status of SONET’s activities in themselves​ or the status of NASA involvement in these activities funded through other means​.
There are no notable FY26 issues or risks to report related to NASA’s support for the SONET project.
There are no non-CUI SONET milestones to report
  Supporting the NASA SR-1 mission sending a nuclear electric power mission to Mars
  SONET funds/manages ~14 projects, including two RPS-simulated sub-kW Stirling demonstration missions, NEP flight demo of 1 kW HEU reactor (partially funded), and tech maturation supporting 100 kW class fission-powered spacecraft systems
  NASA invited to participate in weekly SONET and bi-weekly START meetings
Supported PDR for HEU 1 kWe reactor (KRUSTY-derivative) integrated on a ESPAStar spacecraft (Colossus)
Supported PDR for the Stirling Technology spAce Research experimenT (START) project
Ensured AFRL JETSON/SONET team was invited to NASA FSP and RPS reviews as appropriate.
Maintained a collaborative relationship as both NASA and AFRL pursue technology maturation for space nuclear power.
SONET is a nuclear-technology portfolio at the Air Force Research Laboratory (AFRL) to dramatically expand on-orbit power for USSF operations.
It is a $65M congressional initiative that launched in Q1 of FY26, building on the foundation of a $70M FY22 congressional initiative for the JETSON program.
Developing enabling technologies for integrated functional nuclear-powered spacecrafts
Integrating and demonstrating prototypes to validate models, confirm capabilities, and provide accurate cost estimates for future systems
Catalyzing the commercial industry to foster competition and grow the industrial base
JETSON / SONET | FY26 Review
GO / Space Transportation Annual Review
Project Sponsor | RTMD
Project Manager | George Williams, GRC
Technical Lead | Lee Mason, GRC
Budget Analyst | Larissa Fisher, GRC
FY26 Accomplishments
Project Objectives
U.S. Space Force (USSF) Joint Emergent Technology Supplying On-Orbit Nuclear Power (JETSON) / Space Operations via Nuclear Enhanced Technologies (SONET)
Partnerships / Collaborations
CAD depiction of the 1kWe AFRL Trailblazer
Early lab-level prototype of Stirling Technology spAce Research experimenT (START) by Intuitive Machines (IM)
Artist depiction by Westinghouse ASTRO team for a 20 kWe Fission Spacecraft

## Slide 15
  Prime advisors: Lockheed Martin, Northrop Grumman, Raytheon, BEXT, and Westinghouse
  Partnering with 7 U.S. universities and 10 small businesses
Creating a rich ecosystem of university partners, other world-class research institutions, and small businesses through SSTIs, with a goal of developing revolutionary technologies and transition to employment in operations or industry.
NASA’s primary role in this project is to provide subject matter experts for reviews of various SSTIs, with a current focus on SSTI 3 (of 5), “Advanced Space Power and Propulsion,” which focuses on developing components for a 100-kw nuclear electric propulsion system.
USSF SSTI SPAR | FY26 Review
GO / Space Transportation Annual Review
Project Sponsor | USSF
Project Manager | Eric Pencil, GRC
Technical Lead | Andy Presby, GRC
Budget Analyst | Larissa Fisher, GRC
U.S. Space Force (USSF) Small Spacecraft Technology Initiative (SSTI) Space Power and Propulsion for Agility, Responsiveness, and Resilience (SPAR)
Partnerships / Collaborations
Annual Review | 12/02/26
Upcoming Milestones
PPU: Completed closed loop testing of Dual Active Bridge at scaled voltage and power level.
MPD: Reached record thruster efficiency and exhaust velocity with new MPD thruster head with a low molecular weight gas mixture having wet ASCENT-like atomic composition.
Hall Thruster: Successfully worked with Colorado State University to demonstrate N2 LIF on 8 kW class thruster; performed LIF krypton on thruster up to 50 kW; demonstrated 50 kW thermal steady-state test
Flow System Development: Upgraded low-temperature and high-throughput ASCENT decomposition system implemented and tested.
Chemical Thruster: Design of Gen 1 heterogenous PDT completed
  Small Business SBIR/STTRs in 2025:
    Institute member CisLunar won a Direct-to-Phase II “Interoperable Modular Power Unit for Lightweight and Scalable Electric Propulsion” for $1.9M; effort leverages concepts being developed under SPAR
    Plasma Controls won a Direct-to-Phase II for $1.9M with work related to cathode development under SPAR
    Workforce development: 40+ doctoral and masters students being trained in advanced propulsion, space nuclear systems, power conversion, and advanced orbital dynamics
FY26 Accomplishments

## Slide 16
THRUSTER Demonstrated stable thruster operation with 40% increase in thrust-to-power ratio Manufactured and tested high-throughput carbon ion optics, establishing key performance parameters to support modeling and future flight designs Completed thermal analysis and ion optics lifetime modeling, demonstrating that higher-thrust operation can meet project lifetime goals Manufactured a high-current discharge hollow cathode and initiated a 2,000-hour wear test to demonstrate lifetime capability (test to conclude Oct. 2026) Completed cathode cyclic risk-reduction testing supporting NEXT-C and reducing technical risk for future mission users | POWER PROCESSING UNIT (PPU) Completed fabrication and functional testing of AdvNEXT prototype PPU, incorporating targeted design improvements to reduce system complexity Completed comprehensive PPU environmental testing Successfully completed PPU system integration testing, demonstrating fault-tolerant operation, 92–95% efficiency, and stable performance across all ten operating conditions Completed comprehensive project documentation packages
AdvNEXT | FY26 Review
The AdvNEXT project is a program between NASA, the commercial industry, and USSF to optimize NASA’s Evolutionary Xenon Thruster (NEXT) ion propulsion system for operation at increased thrust-to-power levels.
NEXT was originally developed by NASA’s In-Space Propulsion Technology Program and led by NASA GRC. The NEXT-Commercial (NEXT-C) project was later initiated by NASA in 2015 and led to the development of flight hardware than was demonstrated on the DART mission.
GO / Space Transportation Annual Review
Project Sponsor | USSF
Project Manager | Eric Pencil, GRC
Technical Lead | Rob Thomas, GRC
Budget Analyst | Ben Bauman, GRC
U.S. Space Force (USSF) Interagency Agreement Advanced NEXT (AdvNEXT) Gridded Ion Propulsion
The AdvNEXT system builds upon the NEXT-C architecture, while seeking to reduce parts count, cost, and complexity
Design philosophy is to utilize heritage components wherever practical, to reduce future maturation and qualification costs
AdvNEXT technology is expected to transition to future NASA and partner missions through continued maturation, flight infusion opportunities, & engagement with potential mission and industry users
Technology Description
AdvNEXT PPU during system integration testing
AdvNEXT Throttle Levels: Levels chosen to deliver performance consistent with near-earth applications
End to gridded ion thruster investment: This risks forfeiting a flight-proven NASA propulsion capability, which could:
  Lead to atrophy of workforce, supply-chain, and technical expertise
  Reduce mission design flexibility
  Significantly increase cost and schedule required to reconstitute the technology for future NASA missions
FY26 Issues / Risks
AdvNEXT thruster operation during performance testing
FY26 Accomplishments

## Slide 17
Aerojet Rocketdyne
Busek
Orbion
Lockheed Martin
Vaxon
Aerospace Corporation
AFRL, NRL, AFOSR were also invited as courtesy reviewers
Held final (Year 5) annual review
Application of predictive engineering models (PEMs) to NASA thrusters (NEXT, AEPS)
Over 10 new guidebooks and recommended practices in work for the EP community
Demonstration of the efficacy of novel backsputter reduction devices and materials
Demonstration of new innovative diagnostics to better characterize pressure (neutrals), backsputter transport, and thruster behavior
Application of developed facility models and tools to evaluate new facility design concepts
JANUS Study | FY26 Review
Enabling the flight of high-power electric propulsion (EP) by creating physics-based limits, mitigation techniques, and extrapolation procedures to predict the in-space performance, operation, and lifetime of high-power EP devices from ground tests
Define new standards and requirements for when a test environment is sufficiently “space-like” for high-power EP testing
Develop procedures and techniques for facility design, upgrades, and thruster operation to meet testing requirements
Demonstrate tools and methodologies built on physics-based models to make probabilistic assessments of in-space performance and lifetime based on non-optimal ground tests
Educate the next generation of engineers and scientists in high-power EP
GO / Space Transportation Annual Review
FY26 Accomplishments
Project Sponsor | Catalyst / STRG
Technical Officer | John Yim, GRC
Partnerships / Integrations
Joint Advanced Propulsion Institute (JANUS) Space Technology Research Institute (STRI)
Upcoming Milestones
Outbrief vacuum facility design study | 09/09/26 (TBR)
Delivery of final report | 03/31/27
JANUS grant completion | 03/31/27
NASA’s contribution to this project is through the provision of SME reviewers, and as such, we are not tracking any issues or risks in FY26.
Direct and indirect infusion
Wide dissemination of published work to NASA and EP community
20 PhDs graduated (and 32 more in progress) supported by JANUS who are now at NASA, OGA, industry, and academia
Application of C13 sputter tracking applied to AEPS thruster
Ion thruster PEM applied to evaluate advanced NEXT discharge chamber modifications
Pursuing possible ESI, SBIR, etc. to advance research for direct application for NASA projects (e.g. AMPERE) including future nuclear electric propulsion applications
Transition / Infusion Plans
The JANUS STRI is a collaboration of nine universities, and their industrial advisory board includes representatives from:

## Slide 18
NASA GRC will provide technical consultation and facility usage for the development of the Hyperion low-power electromagnetic AF-MPD thruster.
Hyperion to build a low-power AF-MPD thruster by adapting ideas from SF-MPDs to low-power devices that can efficiently serve next-generation missions and compete with existing HET architectures
AF-MPD is not yet a proven technology
Technology Description
Hyperion
Busek will ship engineering model (EM) or EQM-level thruster to NASA GRC, and NASA will test with Krypton for approximately 4000 hrs.
Team to redesign critical components of AEPS 12 kW HET to increase robustness and reduce cost, part-to-part variability, and duration of fabrication
Rocketdyne
Busek
The 12 kW AEPS thruster provides primary propulsion for PPE/SR-1 Freedom spacecraft
Increasing efficiency of fabrication and robustness of AEPS design has potential to significantly reduce cost of future NASA missions
Technology Description
BHT-600-XL is an extended lifetime version of Busek’s commercial BHT-600 Hall thruster
Duration testing is required to prove the reliability with krypton and reduce risk for Commercial and NASA science mission applications
Technology Description
New ACOs | Project Snapshots
GO / Space Transportation Annual Review
  Primary goals of first integrated device:
  Gain operational experience testing AF-MPDs
  Validate performance and thermal models
  Explore performance at high B fields (>1.0T)
  Busek will deliver thruster, write test plan, analyze data, write report.
  NASA will develop procedures, install thruster, carry out testing, and deliver test reports/data.
Project Objectives
Project Objectives
  Demonstrate additive manufacturing techniques for critical components including the anode and magnetic circuit components
  Conduct tests of improved hollow cathode assembly and assess ability to operate with lower-purity xenon propellant
Project Objectives
Project Sponsor | GO / Space Transportation
Project Manager | Eric Pencil, GRC
Technical Lead | Rob Thomas, GRC
Budget Analyst | Larissa Fisher, GRC
Project Sponsor | GO / Space Transportation
Project Manager | Eric Pencil, GRC
Technical Lead | Drew Ahern, GRC
Budget Analyst | Larissa Fisher, GRC
Project Sponsor | GO / Space Transportation
Project Manager | George Williams, GRC
Technical Lead | Hani Kamhawi, GRC
Budget Analyst | Larissa Fisher, GRC
Announcements of Collaboration Opportunities (ACOs)

## Slide 19: Backups

## Slide 20
Advanced Electric Propulsion (EP) Portfolio | Project Milestones
GO / Space Transportation Annual Review

## Slide 21
Advanced Electric Propulsion (EP) Portfolio | Project Milestones
GO / Space Transportation Annual Review